## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Preparation of DPR for Augmentation of Purba Tajpur Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000154/2022-2023 | 482/SER | 14/07/2022 | 03/08/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.85 | 2.85 | 100 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Augmentation of PURBATAJPUR (ZONE-I) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000187/2022-2023 | 1609/Hug | 05/08/2022 | 14/09/2022 | MS CHANDIMATA CONSTRUCTION | 76.17 | 74.19 | 97.4 | 98
3 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Sinking of 1 no 300 X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of PURBATAJPUR ZONE-II W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000669/2022-2023 | 163/HUG | 16/01/2023 | 15/02/2023 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 12.86 | 12.86 | 100 | 100
4 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1107/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 6.16 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000312/2023-2024 | 1384/9/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 10.9 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Purba Tajpur w/s scheme, P H No 1 |  |  | BILL/04329/2023-2024 | 442 | 24/11/2023 | 24/11/2023 | WBSEDCL | 5.52 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, SERAMPORE SUB-DIVISION, PHE DTE. |  |  | BILL/00738/2023-2024 |  | 06/11/2023 | 06/11/2023 | P. B. ENTERPRISE(PINTU BHADURI) | 1.02 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. |  |  | ORD/001009/2023-2024 | 2502/HMSD | 26/09/2023 | 25/02/2024 | S.P. CONSTRUCTION | 0.72 | 1.16 | 160.84 | 15
9 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR, Switch Rooms, Boundary walls at 2nd TW sites for PURBA TAJPUR (ZONE-I) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000050/2024-2025 | 2339/HUG | 19/06/2024 | 18/08/2024 | TAPAS ADHYA | 28.13 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Augmentation of PURBATAJPUR (ZONE-II) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000465/2022-2023 | 2526/HUG | 23/11/2022 | 02/01/2023 | BIMAL KUMAR HALDER | 76.75 | 67.85 | 88.41 | 98
11 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Purba Tajpur water supply scheme TW No I Block Chanditala II District Hooghly under ED PHED. | Assistant Engineer 1 | Junior Engineer2 | ORD/000223/2022-2023 | 854/ED | 14/02/2023 | 15/05/2023 | A.K. SIKDAR | 10.72 | 10.67 | 99.55 | 99
12 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Left out pipeline to restore the water supply and development of head work site at Purbatajpur Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000896/2023-2024 | 824/HUG | 11/03/2024 | 10/04/2024 | DAS CONSTRUCTION | 22.87 | 22.33 | 97.63 | 95
13 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.02.2024 to 29.02.2024 WB19J-7094 SM Code- 11465 |  |  | BILL/00717/2024-2025 | 229 | 18/06/2024 | 18/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11465 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.01.2024 to 31.01.2024 WB19J-7094 SM Code- 11465 |  |  | BILL/00719/2024-2025 | 228 | 18/06/2024 | 18/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
Total | [13 empty] | 255.17 | 191.91 | 75.21