## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Preparation of DPR for Augmentation of Begampur (Zone- I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000153/2022-2023 | 481/SER | 14/07/2022 | 03/08/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.02 | 4.02 | 99.91 | 0
2 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Quotation bill payment for Begampur w/s scheme |  |  | VCH/002688/2022-2023 |  | 04/11/2022 | 04/11/2022 | WBSEDCL | 0.68 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Begampur Purba Tajpur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001127/2022-2023 | 726/HMSD | 24/03/2023 | 23/04/2023 | ART CONSORTIUM | 3.24 | 3.24 | 100 | 0
4 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001176/2022-2023 | 2043 /ED | 01/12/2022 | 01/03/2023 | BARISAL TRADING CO. | 10.61 | 10.32 | 97.34 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of BEGAMPUR ZONE-II W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000668/2022-2023 | 162/HUG | 16/01/2023 | 15/02/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.66 | 12.54 | 99.03 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of BEGAMPUR ZONE-I W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000667/2022-2023 | 161/HUG | 16/01/2023 | 15/02/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.66 | 12.54 | 99.03 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000306/2023-2024 | 1384/3/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.77 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1107/1/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 6.16 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Quotation Bill for New Service Connection of WBSEDCL for Begampur Kharsari P-II W/S. Sch. |  |  | BILL/00773/2022-2023 | 145 | 30/01/2023 | 30/01/2023 | WBSEDCL | 0.68 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | payment of quotation of wbsedcl bill Begampur w/s scheme z II PH NO III |  |  | BILL/00744/2023-2024 | 33 | 12/05/2023 | 12/05/2023 | WBSEDCL | 0.58 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Payment of Wbsedcl Quotation for Begampur W/S Scheme Zone-I, PH-III |  |  | BILL/00745/2023-2024 | 32 | 12/05/2023 | 12/05/2023 | WBSEDCL | 0.58 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | HIRE CHARGES BILL ASSISTANT ENGINEER, SERAMPORE SUB-DIVISION, PHE DTE. |  |  | BILL/00044/2022-2023 | BP-2022-23-404 | 15/12/2022 | 15/12/2022 | DHIRENDRA ENGINEERING & CONSTRUCTION | 2.36 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply and other allied works at Begampur Water Supply Scheme (Zone-I) within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000782/2023-2024 | 530/HUG | 20/02/2024 | 06/03/2024 | SURAJIT SINGHA RAY | 12.25 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Augmentation of BEGAMPUR (ZONE-II) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division, of Hooghly Division, PHE Dte. . [2nd call of NIeT No. WBPHE/EE/13/HUG/2022-23 Sl No. 02] SL NO - 06 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000237/2022-2023 | 1786/HUG | 26/08/2022 | 25/09/2022 | SURAJIT SINGHA RAY | 26.17 | 20.01 | 76.48 | 30
15 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Begampur water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000199/2022-2023 | 826/ED | 14/02/2023 | 15/05/2023 | CINZANO | 21.49 | 21.49 | 100 | 99
16 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur Kharsarai water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000053/2022-2023 | 2043/ED | 01/12/2022 | 01/03/2023 | BARISAL TRADING CO. | 10.61 | 0.27 | 2.57 | 50
17 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | REGARDING DAMAGE OF PMGSY ROAD 1.027-SONAKA SIDE TO BEGAMPUR PLATFORM VIDE PACKAGE NO.WB08329 IN CHANDITALA-II BLOCK. |  |  | BILL/00181/2024-2025 | BP-2024-25-97 | 02/05/2024 | 02/05/2024 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 9 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | SM/11466 | Augmentation | Augmentation of BEGAMPUR (ZONE-I) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division, of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000424/2022-2023 | 2320/HUG | 02/11/2022 | 02/11/2025 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 245.02 | 192.73 | 78.66 | 25
Total | [13 empty] | 384.55 | 277.17 | 72.08