## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Preparation of DPR for Augmentation of Mandra Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambag]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000244/2022-2023 | 365/Arg | 19/05/2022 | 18/06/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.64 | 3.59 | 98.65 | 0
2 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | New service connection of WBSEDCL for Mandra w/s scheme |  |  | BILL/00798/2022-2023 | 161 | 16/02/2023 |  | WBSEDCL | 0.31 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Quotation Bill for New Service Connection at Mandara W/S. Sch. PH-IV |  |  | BILL/01284/2022-2023 | 190 | 16/03/2023 |  | WBSEDCL | 2.76 | 0 | 0 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIESFOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000348/2022-2023 | 1679/CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 0 | 0 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000351/2022-2023 | 1678/CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1106/1/HUG | 17/04/2023 |  | Resource Division | 13.56 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | New Service Connection at Mandara W/S. Sch. PH-III |  |  | BILL/00725/2023-2024 | 15 | 24/04/2023 |  | WBSEDCL | 9.72 | 0 | 0 | 0
8 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREQW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-IV, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000370/2022-2023 | 1679/ CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 9.51 | 52.55 | 0
9 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-III, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000369/2022-2023 | 1678/ CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 10.73 | 59.29 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 1385/65/Hug | 15/05/2023 |  | Resource Division | 13.13 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of Mandra Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer |  | ORD/000705/2022-2023 | 442/HUG | 16/02/2023 | 17/04/2023 | BENGAL TRADERS | 12.32 | 12.32 | 100 | 100
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of MANDRA W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000665/2022-2023 | 160/HUG | 16/01/2023 | 02/03/2023 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 28.39 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  |  | BILL/00375/2023-2024 | null | 22/08/2023 |  | AATISH KUMAR SHAW | 0.4 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 1688/3/HUG | 22/08/2022 |  | Resource Division | 11.15 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 2209/3/Hug | 30/09/2022 |  | Resource Division | 30.8 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 1773/20/Hug | 29/08/2022 |  | Resource Division | 0.69 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Augmentation of MANDRA Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under Arambagh Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000404/2022-2023 | 2173/HUG | 28/09/2022 | 25/07/2023 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 404.56 | 265.51 | 65.63 | 60
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. V, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000128/2024-2025 | 1153/ED | 14/06/2024 | 12/09/2024 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ATGHARA PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000175/2024-2025 | 1199/ED | 14/06/2024 | 12/09/2024 | EMCON | 10.74 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. VI, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000129/2024-2025 | 1154/ED | 14/06/2024 | 12/09/2024 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mandra water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000038/2023-2024 | 1715/ED | 18/04/2023 | 17/07/2023 | M/S A.K BANERJEE | 21.89 | 21.34 | 97.47 | 75
Total | [13 empty] | 657.93 | 323 | 49.09