## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Preparation of DPR for Augmentation of Mandra Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambag]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000244/2022-2023 | 365/Arg | 19/05/2022 | 18/06/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.64 | 3.59 | 98.65 | 0
2 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIESFOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000348/2022-2023 | 1679/CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 0 | 0 | 0
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000351/2022-2023 | 1678/CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Augmentation of MANDRA Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under Arambagh Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000404/2022-2023 | 2173/HUG | 28/09/2022 | 03/07/2025 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 404.56 | 351.98 | 87 | 60
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREQW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-IV, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000370/2022-2023 | 1679/ CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 9.51 | 52.55 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-III, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000369/2022-2023 | 1678/ CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 18.1 | 10.73 | 59.29 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 1688/3/HUG | 22/08/2022 | 22/08/2022 | Resource Division | 11.15 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 2209/3/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 1773/20/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of MANDRA W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000665/2022-2023 | 160/HUG | 16/01/2023 | 02/03/2023 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 28.39 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of Mandra Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer |  | ORD/000705/2022-2023 | 442/HUG | 16/02/2023 | 17/04/2023 | BENGAL TRADERS | 12.32 | 12.32 | 100 | 100
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mandra water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000038/2023-2024 | 1715/ED | 18/04/2023 | 17/07/2023 | M/S A.K BANERJEE | 21.89 | 21.66 | 98.95 | 75
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1106/1/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 13.56 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 1385/65/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 13.13 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000257/2022-2023 | 127/16/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 10.67 | 0 | 0 | 0
16 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | New service connection of WBSEDCL for Mandra w/s scheme |  |  | BILL/00798/2022-2023 | 161 | 16/02/2023 | 16/02/2023 | WBSEDCL | 0.31 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | New Service Connection at Mandara W/S. Sch. PH-III |  |  | BILL/00725/2023-2024 | 15 | 24/04/2023 | 24/04/2023 | WBSEDCL | 9.72 | 0 | 0 | 0
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Quotation Bill for New Service Connection at Mandara W/S. Sch. PH-IV |  |  | BILL/01284/2022-2023 | 190 | 16/03/2023 | 16/03/2023 | WBSEDCL | 2.76 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  |  | BILL/00375/2023-2024 |  | 22/08/2023 | 22/08/2023 | AATISH KUMAR SHAW | 0.4 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. V, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000128/2024-2025 | 1153/ED | 14/06/2024 | 12/09/2024 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ATGHARA PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer4 | ORD/000175/2024-2025 | 1199/ED | 14/06/2024 | 12/09/2024 | EMCON | 10.74 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Protection works and other allied works at 3rd & 4th TubeWell Site of MANDRA under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000466/2024-2025 | 4048/HUG | 19/12/2024 | 19/03/2025 | MUNSHI TAJUDDIN | 15.5 | 0 | 0 | 0
23 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. VI, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000129/2024-2025 | 1154/ED | 14/06/2024 | 12/09/2024 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | SM/11468 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002644/2024-2025 | 807/Arg | 23/08/2024 | 22/09/2024 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
Total | [13 empty] | 685.09 | 409.79 | 59.82