## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Material Requisition To Resource Division |  |  | RTOR000225/2022-2023 | 109/ 14/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 58.72 | 0 | 0 | 0
2 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Material Requisition To Resource Division |  |  | RTOR000271/2022-2023 | 902/13/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 12.82 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Electrical | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Quotation for new service connection of Sirazpur w/s scheme,PH No-I Dist-Hooghly under ED,PHE Dte |  |  | BILL/02002/2023-2024 | 112 | 19/07/2023 | 19/07/2023 | WBSEDCL | 5.08 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Electrical | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Quotation Bill for New Service Connection at Uttar Sirazpur W/S. Sch. TW-II |  |  | BILL/04327/2023-2024 | 443 | 24/11/2023 | 24/11/2023 | WBSEDCL | 5.56 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of boundary walls at different TW site for SIRAZPUR Piped Water Supply Scheme under Chandannagar Sub-Division , District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000337/2023-2024 | 2420/HUG | 11/08/2023 | 10/10/2023 | M/S T.K.B. CONSTRUCTION | 41.15 | 0 | 0 | 70
6 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Horizontal Auger boring with water jet system Including Approach Road at SIRAZPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000505/2023-2024 | 2903/HUG | 21/09/2023 | 21/10/2023 | M/S T.K.B. CONSTRUCTION | 13.8 | 0 | 0 | 50
7 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of SIRAZPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000670/2022-2023 | 164/HUG | 16/01/2023 | 02/03/2023 | AUXILIARY TUBEWELL DRILLERS | 28.19 | 0 | 0 | 100
8 | HOOGHLY | Haripal | Electrical | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sirazpur water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000121/2022-2023 | 3477/ED | 30/12/2022 | 30/03/2023 | DIPALI CONSTRUCTION | 21.47 | 0 | 0 | 30
9 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of SIRAZPUR Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000709/2022-2023 | 446/HUG | 16/02/2023 | 17/04/2023 | M/S T.K.B. CONSTRUCTION | 12.21 | 0 | 0 | 85
10 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Sirazpur 2nd T/W site & Kolachora PWSS under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000933/2023-2024 | 279/Chan | 15/03/2024 | 30/03/2024 | SUDIPTA SINHA | 0.88 | 0 | 0 | 100
11 | HOOGHLY | Haripal | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME | SM/11580 | New | SIRAZPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 350 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work at HARIPAL Block under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000486/2022-2023 | 2897/HUG | 22/12/2022 | 20/06/2023 | PRASUN ENTERPRISE (PRASUN BISWAS) | 489.75 | 0 | 0 | 19
Total | [13 empty] | 689.62 | 0 | 0