## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | AIMA CHAPSARA Piped Water Supply Scheme with Laying Distribution System, FHTC & Construction of 300 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work at HARIPAL BLOCK under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000485/2022-2023 | 2896/HUG | 22/12/2022 | 18/08/2025 | PRASUN ENTERPRISE (PRASUN BISWAS) | 370.57 | 100.09 | 27.01 | 20
2 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Aima Chapsara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000074/2022-2023 | 3456/ED | 30/12/2022 | 30/03/2023 | TAMAL ENTERPRISE | 21.5 | 21.46 | 99.8 | 30
3 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of AIMA CHAPSARA W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. [2nd Call of WBPHE/EE/35/HUG/2022-23, Sl No-1] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000048/2023-2024 | 1200/HUG | 26/04/2023 | 10/06/2023 | PRASUN ENTERPRISE (PRASUN BISWAS) | 28.83 | 27.45 | 95.23 | 100
4 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of boundary walls at different TW site for AIMACHAPSARA Piped Water Supply Scheme under Chandannagar Sub-Division , District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000338/2023-2024 | 2423/HUG | 11/08/2023 | 01/03/2025 | AMBIAN INFRASTRUCTURE | 41.36 | 3.9 | 9.44 | 50
5 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of AIMA CHAPSARA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000750/2022-2023 | 651/Hug | 10/03/2023 | 09/05/2023 | KAPTON | 12.29 | 12.29 | 100 | 100
6 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Horizontal Auger boring with water jet system Including Culvert ,Approach Road at AIMACHAPSARA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000658/2023-2024 | 3523/HUG | 30/11/2023 | 01/02/2025 | SHREEOM ENTERPRISE | 11.29 | 0 | 0 | 100
7 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Material Requisition To Resource Division |  |  | RTOR000275/2022-2023 | 902/9/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 9.01 | 0 | 0 | 0
8 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Material Requisition To Resource Division |  |  | RTOR000291/2023-2024 | 1383/37/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 9.17 | 0 | 0 | 0
9 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1235/13/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 59.23 | 0 | 0 | 0
10 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-I |  |  | BILL/04474/2023-2024 | 526 | 14/12/2023 | 14/12/2023 | WBSEDCL | 8.35 | 0 | 0 | 0
11 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-II |  |  | BILL/04475/2023-2024 | 525 | 14/12/2023 | 14/12/2023 | WBSEDCL | 2.72 | 0 | 0 | 0
12 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer2 | ORD/000515/2024-2025 | 1645/AE-II/ED | 29/07/2024 | 29/01/2025 | DILIP KUMAR GHOSH | 0.87 | 0.58 | 66.3 | 0
13 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte | Assistant Engineer 2 | Junior Engineer2 | ORD/003371/2023-2024 | 218_AE-II_ED | 20/02/2024 | 20/08/2024 | DILIP KUMAR GHOSH | 0.86 | 0.44 | 50.55 | 0
14 | HOOGHLY | Haripal | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Ayma Chapsara H/W site & Kamarkundu (Zone-VI) 3rd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000284/2024-2025 | 924/Chan | 05/11/2024 | 20/11/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
15 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 |  |  | BILL/02471/2024-2025 | 623 | 18/12/2024 | 18/12/2024 | DILIP KUMAR GHOSH | 0.02 | 0 | 0 | 0
16 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte Car No.- WB-15C-5554 |  |  | BILL/01156/2024-2025 | 281 | 09/07/2024 | 09/07/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
17 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01.09.2024 to 30.09.2024 |  |  | BILL/02107/2024-2025 | 550 | 30/10/2024 | 30/10/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.16 | 0 | 0 | 0
18 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxuary Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-15C-5554 |  |  | BILL/00957/2024-2025 | 266 | 03/07/2024 | 03/07/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
19 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01/10/2024 to 31/10/2024 |  |  | BILL/02472/2024-2025 | 619 | 05/12/2024 | 05/12/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
20 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte 01/07/2024 to 31/07/2024 WB-15C-5554 |  |  | BILL/01639/2024-2025 | 412 | 22/08/2024 | 22/08/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
21 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.- WB-15C-5554 From 01.08.2024 to 31.08.2024 |  |  | BILL/01995/2024-2025 | 468 | 01/10/2024 | 01/10/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
22 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.WB-15C-5554 |  |  | BILL/02106/2024-2025 | 549 | 30/10/2024 | 30/10/2024 | DILIP KUMAR GHOSH | 0.08 | 0 | 0 | 0
23 | HOOGHLY | Haripal | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 |  |  | BILL/02823/2024-2025 | 675 | 28/01/2025 | 28/01/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
Total | [13 empty] | 578.73 | 166.2 | 28.72