## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purushottampur water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000166/2022-2023 | 3500/ED | 30/12/2022 | 30/03/2023 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 21.49 | 19.47 | 90.58 | 80
2 | HOOGHLY | Singur | Hooghly Division | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | PURUSHOTTAMPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000056/2023-2024 | 1251/HUG | 02/05/2023 | 21/09/2025 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 493.06 | 352.66 | 71.52 | 15
3 | HOOGHLY | Singur | Hooghly Division | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Material Requisition To Resource Division |  |  | RTOR000193/2022-2023 | 109/3/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 44.45 | 0 | 0 | 0
4 | HOOGHLY | Singur | Hooghly Division | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Material Requisition To Resource Division |  |  | RTOR000455/2023-2024 | 3058/31/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 10.44 | 0 | 0 | 0
5 | HOOGHLY | Singur | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Quotation Bill for New Service Connection at Purushattampur W/S. Sch. TW-I |  |  | BILL/04244/2023-2024 | 413 | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.4 | 0 | 0 | 0
6 | HOOGHLY | Singur | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Quotation for new service connection at Purushottampur W/S Sch. , T/W No. - II |  |  | BILL/04126/2023-2024 | 381 | 25/10/2023 | 25/10/2023 | WBSEDCL | 2.72 | 0 | 0 | 0
7 | HOOGHLY | Singur | Hooghly Division | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for PURUSHOTTAMPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000399/2024-2025 | 3779/HUG | 25/11/2024 | 22/11/2025 | WATER TECH | 50.34 | 0 | 0 | 30
8 | HOOGHLY | Singur | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Quotation for new service connection at Purushottampur W/S Sch., T/W No. - III,[SM/11582], Molla Simla, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref Id. - 503969446, Dt. - 16-05-25, Application No. - 5004742617 |  |  | BILL/01142/2025-2026 |  | 17/06/2025 | 17/06/2025 | WBSEDCL | 4.17 | 0 | 0 | 0
9 | HOOGHLY | Singur | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | SM/11582 | New | Additional Quotation for Meter/Power shifting with extra pole at Purushottampur W/S Sch., P.H. No. - I, [SM/11582], Block - Singur, Dist - Hooghly, under WBSEDCL, Singur CCC, Ref. Id.- 860368985, Application No. - 100000164005, Dt. - 22/04/2026 |  |  | BILL/00899/2026-2027 |  | 10/06/2026 | 10/06/2026 | WBSEDCL | 0.52 | 0 | 0 | 0
Total | [13 empty] | 630.58 | 372.12 | 59.01