## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  |  | BILL/00081/2022-2023 | null | 27/12/2022 |  | DISTRICT MAGISTRATE HOOGHLY | 215.31 | 0 | 0 | 0
2 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Material Requisition To Resource Division |  |  | RTOR000270/2023-2024 | 1386/49/Hug | 15/05/2023 |  | Resource Division | 10.2 | 0 | 0 | 0
3 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00222/2023-2024 | BP-2023-24-211 | 14/07/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 232.26 | 0 | 0 | 0
4 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00352/2023-2024 | BP-2023-24-295 | 19/08/2023 |  | DISTRICT MAGISTRATE HOOGHLY | 206.54 | 0 | 0 | 0
5 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Mini Piped water Supply Scheme |  |  | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 |  | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
6 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Mini Piped water Supply Scheme |  |  | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 |  | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
7 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Mini piped Water Supply scheme |  |  | BILL/01597/2024-2025 | BILL/01597/2024 | 16/08/2024 |  | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
8 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Mini piped Water Supply scheme |  |  | BILL/01597/2024-2025 | BILL/01597/2024 | 16/08/2024 |  | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
9 | HOOGHLY | Balagarh,Goghat - II,Khanakul - I,Khanakul - II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL - II BLOCK UNDER HOOGHLY DISTRICT (TSM/020222) | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000024/2023-2024 | 1104/HUG | 17/04/2023 | 15/08/2023 | RAJMAHAL ENTERPRISE | 41.84 | 10.07 | 24.07 | 70
Total | [13 empty] | 1861.34 | 10.07 | 0.54