## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Material Requisition To Resource Division |  |  | RTOR000270/2023-2024 | 1386/49/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 10.2 | 0 | 0 | 0
2 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00352/2023-2024 | BP-2023-24-295 | 19/08/2023 | 19/08/2023 | DISTRICT MAGISTRATE HOOGHLY | 206.54 | 0 | 0 | 0
3 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  |  | BILL/00222/2023-2024 | BP-2023-24-211 | 14/07/2023 | 14/07/2023 | DISTRICT MAGISTRATE HOOGHLY | 232.26 | 0 | 0 | 0
4 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  |  | BILL/00081/2022-2023 |  | 27/12/2022 | 27/12/2022 | DISTRICT MAGISTRATE HOOGHLY | 215.31 | 0 | 0 | 0
5 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL - II BLOCK UNDER HOOGHLY DISTRICT (TSM/020222) | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000024/2023-2024 | 1104/HUG | 17/04/2023 | 14/09/2023 | RAJMAHAL ENTERPRISE | 41.84 | 0 | 0 | 70
6 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Muragari Mini PWSS 2. Charsundalpur Mini PWSS 3. Digra Mini PWSS 4. Rampur Mini PWSS 5. Naopara Mini PWSS 6. Telinipara Mini PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000831/2023-2024 | 209/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 45
7 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Mini piped Water Supply scheme |  |  | BILL/01597/2024-2025 |  | 05/08/2024 | 05/08/2024 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
8 | HOOGHLY | Balagarh,Goghat-II,Khanakul-I,Khanakul-II,Pursura | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | SM/11583 | New | Mini Piped water Supply Scheme |  |  | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 16/08/2024 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
Total | [13 empty] | 1284.7 | 0 | 0