## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Preparation of DPR for Augmentation of Bagnan Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000562/2021-2022 | 130/CH | 17/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.03 | 4.01 | 99.46 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 180 M at Proposed TW site of Badinan W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000141/2022-2023 | 1412/HUG | 12/07/2022 | 11/08/2022 | OSMAN SEKH | 9.29 | 8.93 | 96.12 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Repair and Renovation of R.C.C Elevated Reservoir & Balance FHTC for augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000600/2022-2023 | 2859/HUG | 16/12/2022 | 30/01/2023 | M/S RAJKUMAR KHAN | 41 | 40.49 | 98.76 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bagnan water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000195/2022-2023 | 822/ED | 14/02/2023 | 15/05/2023 | A.S. ENTERPRISE | 21.45 | 18.52 | 86.33 | 30
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000788/2022-2023 | 883/HUG | 27/03/2023 | 11/05/2023 | B.K ENTERPRISE | 75.32 | 28.3 | 37.57 | 80
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Proposed Laying Distribution within Noapara & Bagnan Mouza & Repairing Of Switch Room of Existing T.W-1 & T.W-2 for Augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000580/2022-2023 | 2902/HUG | 23/12/2022 | 23/03/2023 | TOTON MONDAL | 103.85 | 102.37 | 98.58 | 100
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000273/2023-2024 | 1386/50/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 3.28 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000223/2022-2023 | 226/Hug | 24/01/2023 | 24/01/2023 | Resource Division | 2.85 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Quotation Bill foe New Service Connection at Bagnan W/S. Sch. Z-II |  |  | BILL/02587/2023-2024 | 158 | 03/08/2023 | 03/08/2023 | WBSEDCL | 3.74 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Quotation Bill for New Service Connection at Bagnan W/S. Sch. Z-II |  |  | BILL/02590/2023-2024 |  | 01/08/2023 | 01/08/2023 | WBSEDCL | 10.74 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | QUOTATION FOR WBSEDCL FOR ELECTRICAL DIVISION, PHE DTE. |  |  | VCH/001389/2022-2023 | C112223783044 | 21/11/2022 | 21/11/2022 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.2 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Quotation bill for new service connection charge at Bagnan w/s scheme, Zone-II, T.W. No.-I |  |  | BILL/02725/2023-2024 | 182 | 11/08/2023 | 11/08/2023 | WBSEDCL | 10.74 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Proposed AUGMENTATION of BAGNAN Zone-II Piped Water Supply Scheme with Laying Distribution System , FHTC & Construction of 1 No 3.6 M X 3.0 M Switch Room with Sanitary and Water Supply Arrangements &Boundary wall at Proposed T.W Site at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000601/2022-2023 | 2860/HUG | 16/12/2022 | 30/01/2023 | M/S ROY CONSTRUCTION AND CO. | 35.29 | 0 | 0 | 35
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Proposed Laying Distribution within Kanuibanka Mouza , FHTC& Repairing Of Boundary Wall of Existing T.W-1 & T.W-2 for Augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000605/2022-2023 | 2891/HUG | 22/12/2022 | 20/02/2023 | M/S.N. ISLAM AND CO. | 85.47 | 81.31 | 95.13 | 70
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas of BAGNAN ZONE-I (Bagnan, Khanpur, Balarambati, Noapara, Mihirpur) PWSS under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000339/2023-2024 | 2426/HUG | 11/08/2023 | 10/09/2023 | TOTON MONDAL | 19.11 | 22.89 | 119.8 | 98
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of BAGNAN Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000599/2023-2024 | 3314/HUG | 10/11/2023 | 25/12/2023 | SRI KRISHNA ENTERPRISE | 8.61 | 16.78 | 194.8 | 95
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Bhuina Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000767/2023-2024 | 121/CH | 16/02/2024 | 02/03/2024 | TOTON MONDAL | 4.79 | 9.3 | 194.32 | 95
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Brahman Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000768/2023-2024 | 122/CH | 16/02/2024 | 02/03/2024 | JOY GURU ENTERPRISE | 4.79 | 9.23 | 192.68 | 95
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Kayastha Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000769/2023-2024 | 126/CH | 16/02/2024 | 02/03/2024 | JOY GURU ENTERPRISE | 4.79 | 9.33 | 194.92 | 95
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Bagnan PWSS 2. Bhanderhati PWSS 3. Cheragram PWSS 4. Chopa PWSS 5. Dhamaitikri PWSS 6. Dhaniakhali PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000825/2023-2024 | 203/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Sinking of 1 no. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BAGNAN W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000895/2023-2024 | 819/HUG | 11/03/2024 | 10/04/2024 | TAPAS ADHYA | 14.7 | 13.9 | 94.55 | 100
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Shifting of Pipeline in damaged portion including providing FHTC at the left out portions of Bagdi Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000044/2024-2025 | 546/CH | 14/06/2024 | 21/06/2024 | TOTON MONDAL | 4.79 | 4.69 | 97.95 | 95
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Shifting of Pipeline in damaged portion including providing FHTC at the left out portions of Pritala area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000045/2024-2025 | 547/CH | 14/06/2024 | 21/06/2024 | JOY GURU ENTERPRISE | 4.79 | 4.73 | 98.78 | 95
24 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Bagnan T/W-V W/S scheme under Electrical Division PHE Dte. (SM/11867) |  |  | BILL/02294/2024-2025 | BP-24-25-599 | 21/11/2024 | 21/11/2024 | WBSEDCL | 5.92 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | SM/11867 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BELMURI GP of DHANIAKHALI Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000929/2023-2024 | 247/CH | 12/03/2024 | 13/01/2025 | SUNITI MAIRA | 4.95 | 0 | 0 | 90
Total | [13 empty] | 488.43 | 375.73 | 76.93