## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Preparation of DPR for Augmentation of Srikrishnapur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000564/2021-2022 | 145/CH | 21/02/2022 | 28/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.76 | 4.73 | 99.33 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000232/2022-2023 | 226/9/Hug | 24/01/2023 |  | Resource Division | 33.67 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000295/2023-2024 | 1386/57/Hug | 15/05/2023 |  | Resource Division | 13.9 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with LDS within South East, providing FHTC & Construction of Boundary Wall, Internal Pathway at 2nd TW Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000598/2022-2023 | 2857/HUG | 16/12/2022 | 14/02/2023 | MS PRADIP KUMAR PAL | 77.87 | 56.48 | 72.53 | 0
5 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II |  |  | BILL/02594/2023-2024 | null | 01/08/2023 |  | WBSEDCL | 4.91 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II |  |  | BILL/02593/2023-2024 | 156 | 03/08/2023 |  | WBSEDCL | 3.84 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Quotation bill for new service connection charge at Srikrishnapur w/s scheme, T.W. No.-II |  |  | BILL/02726/2023-2024 | 181 | 11/08/2023 |  | WBSEDCL | 4.91 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000788/2022-2023 | 883/HUG | 27/03/2023 | 11/05/2023 | B.K ENTERPRISE | 75.32 | 0 | 0 | 80
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with LDS Within West portion, providing FHTC & Construction of Boundary Wall, Internal Pathway at H/W Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000599/2022-2023 | 2858/HUG | 16/12/2022 | 14/02/2023 | SAMRAT CONSTRUCTION | 87.74 | 61.98 | 70.64 | 20
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Hiring of Luxury Car (BS-IV) for the Official us of the Executive Engineer, Electrical Division PHED wef 01.06.23 to 30.11.23 |  |  | ORD/001022/2023-2024 | 363_AE-I_ED | 29/05/2023 | 28/05/2024 | TRIDIP SARKAR | 5 | 1 | 19.94 | 40
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-I) Piped Water Supply Scheme with Laying Distribution System Within Srikrishnapur Mouza(Part), providing FHTC & repairing of of Switch Room (3.6 M x 3.0M) & Boundary wall at existing 2nd T.W Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000596/2022-2023 | 2855/HUG | 16/12/2022 | 14/02/2023 | DAS TRADING | 78.15 | 54.42 | 69.64 | 75
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with Laying Distribution System Within South West, providing FHTC & Construction of 1 No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements at Head Work Site at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000604/2022-2023 | 2890/HUG | 22/12/2022 | 20/02/2023 | G.S CONSTRUCTION AND CO. | 61.25 | 32.08 | 52.38 | 67
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Srikrishnapur water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | Assistant Engineer 2 | Junior Engineer1 | ORD/000229/2022-2023 | 860/ED | 14/02/2023 | 15/05/2023 | ASHUTOSH DAS & CO. | 21.49 | 10.45 | 48.64 | 50
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (ZONE-I) Piped Water Supply Scheme with Laying Distribution System Within Dasghara G.P., providing FHTC & repairing of of 272 cum capacity RCC OHR, Boundary Wall, Switch Room at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000595/2022-2023 | 2854/HUG | 16/12/2022 | 14/02/2023 | SWASTIK ENTERPRISE | 72.14 | 67.11 | 93.03 | 75
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Superstructure part as per Departmental Drawing), pipe connection and cost of pipes & specials with necessary soil investigation with foundation design as per soil test report For AUGMENTATION of SRIKRISHNAPUR ZONE-II & its adjoining moujas water supply Scheme within DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division, P.H.E.Dte. Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000023/2023-2024 | 1103/HUG | 17/04/2023 | 14/10/2023 | M/S SHIVAM UDYOG | 93.02 | 29.77 | 32 | 70
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-I) Piped Water Supply Scheme with Laying Distribution System Within Srikrishnapur Zone-I (North), providng FHTC & Construction of 3.6m x3.0 m Switch Room at Zone-II at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000597/2022-2023 | 2856/HUG12 | 16/12/2022 | 14/02/2023 | DILIP KUMAR GHOSH | 68.2 | 59.71 | 87.56 | 80
Total | [13 empty] | 795.53 | 377.73 | 47.48