## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Preparation of DPR for Augmentation of Cheragram Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000563/2021-2022 | 146/CH | 21/02/2022 | 28/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.48 | 4.44 | 99.2 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2023-2024 | 1386/13/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 13.66 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000534/2023-2024 | 3059/33/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.66 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000233/2022-2023 | 226/4/Hug | 24/01/2023 | 24/01/2023 | Resource Division | 20.31 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Cheragram water supply scheme, T.W. No.- I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000204/2022-2023 | 831/ED | 14/02/2023 | 15/05/2023 | INDRAJIT MITRA | 10.98 | 10.68 | 97.28 | 57
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Sinking of 1 no. 300 X200 mm dia Replacement Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Cheragram W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000670/2023-2024 | 3593/HUG | 05/12/2023 | 04/01/2024 | OSMAN SEKH | 16.05 | 0 | 0 | 100
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Quotation Bill for New Service Connection at Cheragram W/S. Sch. |  |  | BILL/05063/2023-2024 | 683 | 19/01/2024 | 19/01/2024 | WBSEDCL | 13.03 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/001550/2024-2025 | 323/HUG | 05/02/2025 | 02/03/2025 | SWARNA ENTERPRISE | 8.63 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | SM/11924 | Augmentation | Construction of 2 Nos. 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation in ZONE-I & II, Sinking of tube-well, LDS, Rising Main, FHTC, construction of switch-room & boundary wall in ZONE-I & Repairing of Existing Switch Rooms, Boundary walls at different TW sites of both zones, LDS, Rising Main, FHTC in ZONE-II for Augmentation of CHERAGRAM Piped Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000724/2022-2023 | 561/HUG | 27/02/2023 | 02/05/2025 | TAPU SAHA | 543.92 | 410.67 | 75.5 | 98
Total | [13 empty] | 644.71 | 425.79 | 66.04