## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Preparation of DPR for Augmentation of Raghunathpur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) |  | ORD/000565/2021-2022 | 129/CH | 17/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.13 | 4.12 | 99.76 | 0
2 | HOOGHLY |  | Central Drilling | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DIOSTRICT UNDER CDD, PHE DTE | Driller In Charge | Junior Engineer | ORD/000121/2022-2023 | 289/CMSD-II (D) | 01/06/2022 | 16/06/2022 | C.M. ENTERPRISE | 4.99 | 4.73 | 94.84 | 0
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000122/2022-2023 | 288/CDD | 01/06/2022 | 16/06/2022 | C.M. ENTERPRISE | 3.07 | 2.9 | 94.36 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | SUPPLY & DELIVERY CONSUMBLES SITE FOR CONSTRUCTION OF TUBE WELL AT RAGHUNATHPUR W/S SCH TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000123/2022-2023 | 290/CMSD-II (D) | 01/06/2022 | 16/06/2022 | C.M. ENTERPRISE | 2.45 | 2.4 | 97.99 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Special Repairing, maintenance work of damaged R.C.C. Elevated Reservoir of Capacity 1,36,200 litre of Raghunathpur & Damra Water Supply Scheme under Chinsurah Sub - Division of Hooghly Division, P.H.E. Dte. SL NO - 03 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000285/2022-2023 | 1906/HUG | 05/09/2022 | 20/10/2022 | M/S SHIVAM UDYOG | 25.15 | 25.12 | 99.88 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | 2nd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.12.2022 to 31.12.2022 under Chinsurah Sub- Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000494/2022-2023 | 2593/HUG | 30/11/2022 | 31/12/2022 | M/S BISWAS CONSTRUCTION | 0.49 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Augmentation of Raghunathpur (ZONE-II) with LDS, FHTC, Laying Rising Main & Interconnection with Distribution system at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000384/2022-2023 | 1572/HUG | 01/08/2022 | 10/09/2022 | DAS ENTERPRISE (SAMIR DAS) | 96.59 | 87.61 | 90.7 | 50
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-I Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000707/2022-2023 | 444/HUG | 16/02/2023 | 02/04/2023 | SHREEOM ENTERPRISE | 6.29 | 6.29 | 100 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | 3rd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.01.23 to 31.08.22 under Chinsurah Sub- Division P.H.E Dte. SL-15 | Assistant Engineer (Civil) |  | ORD/000817/2022-2023 | 2974/HUG | 30/12/2022 | 30/08/2023 | M/S BISWAS CONSTRUCTION | 3.96 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RAGHUNATHPUR(Zone-I) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 01 | Assistant Engineer (Civil) |  | ORD/000339/2022-2023 | 1953/HUG | 07/09/2022 | 22/10/2022 | ARUN SEAL AND CO. | 23.79 | 23 | 96.67 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RGHUNATHPUR(Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 02 | Assistant Engineer (Civil) |  | ORD/000340/2022-2023 | 1954/HUG | 07/09/2022 | 22/10/2022 | DAS ENTERPRISE (SAMIR DAS) | 23.78 | 22.92 | 96.37 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000708/2022-2023 | 445/HUG | 16/02/2023 | 17/04/2023 | DAS TRADING | 12.25 | 12.25 | 100 | 100
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Dismantaling of old damaged Switch room at Ragunathpur 3rd Tube well site of Agumentation of Raghunathpur W/S Scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000303/2023-2024 | 690/CH | 27/07/2023 | 06/08/2023 | SRI KRISHNA ENTERPRISE | 0.31 | 0.31 | 98.98 | 100
14 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Assistant Chief Engineer (M/E), PHE Dte. |  |  | ORD/002165/2022-2023 | 2382/HMSD | 27/12/2022 | 27/04/2023 | BHOLA DEY | 1.11 | 1.11 | 100 | 1
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 2211/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 0.05 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000284/2023-2024 | 1383/31/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 17.69 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000230/2022-2023 | 226/8/Hug | 24/01/2023 | 24/01/2023 | Resource Division | 59.6 | 0 | 0 | 0
18 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - I |  |  | BILL/00780/2023-2024 | 52 | 31/05/2023 | 31/05/2023 | WBSEDCL | 8.32 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - IV |  |  | BILL/00778/2023-2024 | 52 | 31/05/2023 | 31/05/2023 | WBSEDCL | 5.95 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - II |  |  | BILL/00781/2023-2024 | 52 | 31/05/2023 | 31/05/2023 | WBSEDCL | 2.64 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - III |  |  | BILL/00777/2023-2024 | 52 | 31/05/2023 | 31/05/2023 | WBSEDCL | 6.07 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Raghunathpur water supply scheme TW No I II III and IV, Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000224/2022-2023 | 855/ED | 14/02/2023 | 15/05/2023 | D. K. ELECTRIC | 42.97 | 42.89 | 99.81 | 95
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of RAGHUNATHPUR Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000600/2023-2024 | 3315/HUG | 10/11/2023 | 25/12/2023 | DIBYENDU DHARA | 8.56 | 7.98 | 93.25 | 65
24 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001388/2023-2024 | 4738/ED | 15/12/2023 | 14/03/2024 | S. DUTTA | 10.74 | 0 | 0 | 90
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Shifting House Connection from existing main to new main and allied works from Bispara to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000030/2024-2025 | 532/CH | 14/06/2024 | 21/06/2024 | R.K. TRADERS | 4.85 | 0 | 0 | 75
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Shifting House Connection from existing main to new main and allied works from Kuntighat More of Bispara of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000039/2024-2025 | 541/CH | 14/06/2024 | 21/06/2024 | R.K. TRADERS | 4.84 | 0 | 0 | 75
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Shifting HDPE pipeline and allied works from Kuntighat to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000040/2024-2025 | 542/CH | 14/06/2024 | 21/06/2024 | R.K. TRADERS | 3.15 | 0 | 0 | 75
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Augmentation of Raghunathpur (ZONE-I) with LDS, FHTC, Rising Main & Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000403/2022-2023 | 2172/HUG | 28/09/2022 | 09/07/2026 | PRADIP KUMAR ADHYA | 433.19 | 235.24 | 54.3 | 55
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Laying HDPE Pipeline From existing Distribution System for providing FHTC at Raghunathpur Z-II W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001850/2024-2025 | 229/CH | 19/02/2025 | 16/06/2025 | DAS ENTERPRISE (SAMIR DAS) | 4.46 | 0 | 0 | 50
30 | HOOGHLY |  | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Qutation of service connection for Raghunathpur [SM/11969] W/S Supply Scheme, Block - Chinsurah-Mogra, Dt. - Hooghly, Ref ID. - 503899158, Application No. - 5004617945, Dt. - 11-03-2025 |  |  | BILL/00743/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 21.6 | 0 | 0 | 0
Total | [13 empty] | 843.04 | 478.88 | 56.8