## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Tilari, Dwaripara, Kakand Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000591/2022-2023 | 2850/HUG | 16/12/2022 | 15/01/2023 | TANISA ENTERPRISE | 23.9 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Fului Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000589/2022-2023 | 2848/HUG | 16/12/2022 | 30/01/2023 | TITAS CONSTRUCTION | 47.25 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Badanganj Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000611/2022-2023 | 2922/HUG | 27/12/2022 | 26/01/2023 | MS K.B CONSTRUCTION | 30.75 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Shyambazar Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000594/2022-2023 | 2853/HUG | 16/12/2022 | 30/01/2023 | MS K.B CONSTRUCTION | 51.48 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1106/3/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 15.88 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Betra Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000590/2022-2023 | 2849/HUG | 16/12/2022 | 15/01/2023 | KOUSIK MONDAL | 25.28 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Kayapat, Shyampur, Tilati, Chakran Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000592/2022-2023 | 2851/HUG | 16/12/2022 | 30/01/2025 | I R CONSTRUCTION | 37.54 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | SM/11990 | Retrofitting | Laying balance pipeline and other allied works at Badangnj and Fului village within Badanganj Zone - I PWSS under Arambagh Sub Division, PHE Dte. Hooghly |  |  | ORD/002317/2024-2025 | 663/HUG | 11/03/2025 | 25/04/2025 | TITAS CONSTRUCTION | 39.19 | 0 | 0 | 0
Total | [13 empty] | 271.28 | 0 | 0