## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Supply and Delivary of Water Testing Chemical and Other Consumable Requirement of 9 nos Water Testing Laboratories for 3 Months in Hooghly District under Hooghly Division PHE Dte. | Assistant Engineer(HQ) |  | ORD/000383/2022-2023 | 109/HQ/HUG | 29/06/2022 | 02/07/2022 | LAB SOLUTION | 2.08 | 2.08 | 100 | 0
2 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Work Order for the Chemical requirement for habitation wise Arsenic Testing Special Drive, Hooghly Division, P.H.E. Dte. [SL NO. 01] | Assistant Engineer(HQ) |  | ORD/000621/2022-2023 | 254/HQ/HUG | 21/10/2022 | 31/10/2022 | A.R. CONSTRUCTION | 0.49 | 0.49 | 100 | 0
3 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Chemical Requirement for Habitation Wise Arsenic Testing Special Drive, Hooghly Division, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/000685/2022-2023 | 25/HQ/HUG | 17/01/2023 | 22/01/2023 | R CONSTRUCTION | 0.94 | 0.94 | 100 | 0
4 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Chemical Requirement for Habitation Wise Arsenic Testing Special Drive, Hooghly Division, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/000684/2022-2023 | 24/HQ/HUG | 17/01/2023 | 22/01/2023 | R CONSTRUCTION | 0.94 | 0.94 | 100 | 0
5 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | Assistant Engineer(HQ) |  | ORD/000569/2023-2024 | 309/HQ/HUG | 02/09/2023 | 12/09/2023 | DAS TRADING | 0.75 | 0.67 | 89.2 | 98
6 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. | Assistant Engineer(HQ) |  | ORD/000797/2022-2023 | 933/HUG | 29/03/2023 | 18/04/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 5.91 | 5.91 | 100 | 99
7 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Engagement of resources person for supervision of SURVELLIANCE AUDIT the protocol / standard operating procedures/ technical documentation of laboratory water testing activities as per ISO/IEC 17025:2017 including performing statutory internal audit, refresher course and any other required laboratory management process and allied works to comply NABL accreditation retention system of Hooghly District Water testing Laboratory, PHE Dte for a period of four months. | Assistant Engineer(HQ) |  | ORD/000047/2023-2024 | 1180/Hug | 24/04/2023 | 22/08/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.77 | 2.77 | 100 | 99
8 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Supply of required CRMs for upcoming Surveillance Audit by NABL to maintain ISO/IEC 17025:2017 Accreditation status of Hooghly Dist. Water Testing Laboratory under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal | Assistant Engineer(HQ) |  | ORD/000394/2023-2024 | HQ/HUG/281 | 11/08/2023 | 16/08/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.58 | 0.58 | 100 | 95
9 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Supply and delivery chemical requirement for Amartya Rural Welfare & Research Centre Water Testing Laboratory at Balagarh Block under Hooghly Division, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/000568/2023-2024 | 348/HQ/HUG | 11/10/2023 | 21/10/2023 | LAB SOLUTION | 0.42 | 0.42 | 100 | 100
10 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Chemical and others consumable requirement of Kamarpukur Sub - District Water Testing Laboratory for one month under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000677/2023-2024 | 401/HQ/HUG | 08/12/2023 | 18/12/2023 | LAB SOLUTION | 0.73 | 0.73 | 100 | 100
11 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001813/2024-2025 | 234B/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.96 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001812/2024-2025 | 234A/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.83 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | 3rd Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD : 3 MONTHS (01.04.2024 TO 30.06.2024) | Assistant Engineer(HQ) |  | ORD/001565/2023-2024 | 74/HQ/HUG | 28/03/2024 | 27/06/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Engagement of 3 personnel (Chemist / Bacteriologist / Lab Assistant) in Chandanagar Sub District Water Testing Laboratory II under Hooghly Division PHE Dte For a period of 8 Months. | Assistant Engineer (Civil),Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000267/2023-2024 | 2242/HUG | 01/08/2023 | 02/11/2024 | CLIFFORD FACILITY SERVICES PVT LTD. | 5.91 | 3.08 | 52.13 | 100
15 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Engagement of 5 personnel (Sampling Assistant / Lab Attendant) in Water Testing Laboratories under Hooghly Division PHE Dte. for a period of 4 Months. | Assistant Engineer (Civil),Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000438/2023-2024 | 2632/HUG | 31/08/2023 | 01/12/2024 | CLIFFORD FACILITY SERVICES PVT LTD. | 4.91 | 0.97 | 19.83 | 100
16 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | Engagement of 2 personnel (Chemist/Bacteriologist and One lab Assistant) in each of 03 new water testing laboratories under Hooghly Division PHE Dte for a period of 2 Months. | Assistant Engineer (Civil),Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000440/2023-2024 | 2633/HUG | 31/08/2023 | 01/09/2024 | CLIFFORD FACILITY SERVICES PVT LTD. | 8.42 | 8.42 | 100 | 100
17 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | 2nd Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD : 3 MONTHS (01.01.2024 TO 31.03.2024) | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001564/2023-2024 | 433/HQ/HUG | 29/12/2023 | 29/03/2024 | DAS TRADING | 0.75 | 0 | 0 | 100
18 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | NGO MAINTAINED LABORATORY REMUNERATION FOR THE MONTH OF SEPTEMBER 2025 UNDER HOOGHLY DIVISION, P.H.E.DTE. |  |  | BILL/01352/2025-2026 |  | 04/11/2025 | 04/11/2025 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | NGO MAINTAINED LABORATORY REMUNERATION FOR THE MONTH OF SEPTEMBER 2025 UNDER HOOGHLY DIVISION, P.H.E.DTE. |  |  | BILL/01354/2025-2026 |  | 04/11/2025 | 04/11/2025 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR | SM/11996 | Support-WQMSP | NGO MAINTAINED LABORATORY REMUNERATION FOR THE MONTH OF MAY 2025 UNDER HOOGHLY DIVISION, P.H.E.DTE. |  |  | BILL/01353/2025-2026 |  | 04/11/2025 | 04/11/2025 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
Total | [13 empty] | 39.67 | 28 | 70.57