## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME | SM/11998 | Retrofitting | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of HAZIPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000339/2021-2022 | 16/Hug | 04/01/2022 | 03/02/2022 | M/S T.K.B. CONSTRUCTION | 19.85 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME | SM/11998 | Retrofitting | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of HAZIPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000007/2023-2024 | 1013/Hug | 06/04/2023 | 25/01/2025 | RITAM ENTERPRISE | 11.79 | 0 | 0 | 100
Total | [13 empty] | 31.65 | 0 | 0