## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000906/2023-2024 | 829/HUG | 11/03/2024 | 10/04/2024 | SURAJIT SINGHA RAY | 30.4 | 30.4 | 100 | 99
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Lohagachhi village under Antpur PWSS (2 nos.) 2. Ranibazar village under Antpur PWSS (2 nos.) 3. Anarbati village under Antpur PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000957/2023-2024 | 170/SER | 11/03/2024 | 18/03/2024 | TOTON MONDAL | 0.95 | 0.95 | 100 | 80
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Raipur village under Antpur PWSS (2 nos.) 2. Atpur village under Antpur PWSS (2 nos.) 3. Palgachha village under Antpur PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000959/2023-2024 | 171/SER | 11/03/2024 | 18/03/2024 | TOTON MONDAL | 0.95 | 0.95 | 100 | 80
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Repairing of Damaged Road due to FHTC Works at Ranibazar & Lohagacchi mouzas of Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000204/2024-2025 | 549/SER | 19/09/2024 | 26/09/2024 | TOTON MONDAL | 4.99 | 0 | 0 | 98
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Providing 1250 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Antpur Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000913/2020-2021 | 466/HUG | 26/02/2021 | 01/01/2024 | GHOSH CONCERN | 96.72 | 4.55 | 4.7 | 72
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Repairing of Damaged Road due to FHTC Works at Tara mouza of Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000188/2024-2025 | 531/SER | 17/09/2024 | 01/10/2024 | BIMAL KUMAR HALDER | 5 | 2.61 | 52.31 | 99
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Repairing of Damaged Road due to FHTC Works at Bamnagar & Raipur mouzas of Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000189/2024-2025 | 532/SER | 17/09/2024 | 04/10/2024 | BIMAL KUMAR HALDER | 5 | 0 | 0 | 96
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | SM/12000 | Retrofitting | Repairing of Damaged Road due to FHTC Works at Bamnagar mouza of Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000190/2024-2025 | 533/SER | 17/09/2024 | 30/12/2024 | SURAJIT SINGHA RAY | 4.99 | 1.32 | 26.36 | 99
Total | [13 empty] | 149 | 40.78 | 27.37