## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | SM/12002 | Retrofitting | Providing 1102 nos Functional Household Tap Connection (FHTC) within Paschim Thakurani Chak Mouza of PurbaThakurani Chak (Zone-I)Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000060/2022-2023 | 888./HUG | 29/04/2022 | 08/06/2022 | DIPTI TRADERS | 52.17 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | SM/12002 | Retrofitting | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System of PURBATHAKURANICHAK ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer |  | ORD/000237/2023-2024 | 1157/Hug | 20/04/2023 | 20/05/2023 | SUDIPTA SINHA | 6.7 | 0 | 0 | 10
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | SM/12002 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of PURBA THAKURANICHAK ZONE-I PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000109/2023-2024 | 1429/HUG | 18/05/2023 | 02/07/2023 | MA CONSTRUCTION | 28.31 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | SM/12002 | Retrofitting | Construction of Boundary Wall, Internal Pathway & Land development at the Head Work Site of PURBA THAKURANICHAK ZONE-II Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000540/2022-2023 | 2741/HUG | 07/12/2022 | 21/01/2023 | DILIP KUMAR GHOSH | 13.62 | 0 | 0 | 50
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | SM/12002 | Retrofitting | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System of PURBATHAKURANICHAK ZONE-II Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte | Assistant Engineer |  | ORD/000043/2023-2024 | 1158/HUG | 20/04/2023 | 20/05/2023 | RANA ENTERPRISE | 7.31 | 0 | 0 | 95
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | SM/12002 | Retrofitting | Sinking of 3 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PURBO THAKURANICHAWK , RAJHATO , KAKNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000169/2024-2025 | 3167/HUG | 10/09/2024 | 18/05/2025 | MONDAL PRECISION PRIVATE LIMITED | 48.47 | 0 | 0 | 66
Total | [13 empty] | 156.58 | 0 | 0