## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME | SM/12014 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in Chiladangi PWSS, Block Pursurah under Arambag Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer |  | ORD/000244/2023-2024 | 2099/HUG | 19/07/2023 | 02/09/2023 | ARATI ENGINEERING | 94.38 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME | SM/12014 | Retrofitting | Supply of 200 mm dia CD pipe for Sinking of Tubewell at CHILADANGI Piped W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/001547/2025-2026 | 329/Arg, | 04/04/2025 | 11/04/2025 | MAYA CONSTRUCTION | 0.97 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME | SM/12014 | Retrofitting | Supply of 200 mm dia CD pipe for Sinking of Tubewell at CHILADANGI Piped W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/001548/2025-2026 | 329A/Arg, | 04/04/2025 | 11/04/2025 | MAYA CONSTRUCTION | 0.97 | 0 | 0 | 0
Total | [13 empty] | 96.31 | 0 | 0