## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | SM/12015 | Retrofitting | Preparation & Improvement of foundation due to continuous comprehensive seepage after starting of excavation for raft foundation at Head Work Site of HARADITYA Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/000434/2022-2023 | 739/Arg | 29/09/2022 | 29/10/2022 | ANUP PAUL | 1.48 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | SM/12015 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of HARADITYA PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000106/2023-2024 | 1426/HUG | 17/05/2023 | 01/07/2023 | GANESH RAY | 37.07 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | SM/12015 | Retrofitting | Providing 1319 nos Functional Household Tap Connection (FHTC) within Haraditya & Shyamgram Village of Haraditya Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000055/2022-2023 | 884/HUG | 29/04/2022 | 08/06/2022 | ANUP PAUL | 62.53 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | SM/12015 | Retrofitting | Providing 1301 nos Functional Household Tap Connection (FHTC) within Amgaon, Birati & Chhandra Village of Haraditya Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000056/2022-2023 | 885/HUG | 29/04/2022 | 08/06/2022 | PREMANANDA ROY BISWAS | 58.31 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | SM/12015 | Retrofitting | Construction of Boundary Wall, Internal Pathway at 2nd TW Site of HARADITYA Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000538/2022-2023 | 2739/HUG | 07/12/2022 | 06/01/2023 | S.D ENTERPRISE (SAMIR KR. DAS) | 4.87 | 0 | 0 | 100
Total | [13 empty] | 164.26 | 0 | 0