## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Preparation of DPR for Augmentation of Ghoradaha Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000100/2022-2023 | 390/Arg | 31/05/2022 | 30/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 3.34 | 79.17 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 1385/21/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.81 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1234/10/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 17.59 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Quotation for New Service Connection of Goradaha w/s Scheme,TW No-3 Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte |  |  | BILL/03627/2023-2024 | 220 | 25/08/2023 | 25/08/2023 | WBSEDCL | 6.53 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Quotation Bill for New Service Connection at |  |  | BILL/04140/2023-2024 | 390 | 02/11/2023 | 02/11/2023 | WBSEDCL | 8.75 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme with Construction of Boundary wall at 1st T.W Site, Repairing of Switch room, Laying of Rising main with necessary interconnection with T.W. & Distribution System & Functional Household tap Connection under Arambag SUb-Division of Hooghly Division, PHE Dte. within Khanakul -II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000716/2022-2023 | 493/HUG | 20/02/2023 | 21/05/2023 | DILIP KUMAR GHOSH | 149.07 | 110.91 | 74.4 | 25
7 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme by Sinking of 2 Nos. Tube well, Laying Distribution System, Construction of 2 Nos. Switch Room at 3rd & 4th Tubewell site and Boundary wall at 2nd, 3rd & 4th Tubewell site under Arambag Sub-Division of Hooghly Division PHE Dte. within Khanakul - II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000702/2022-2023 | 396/HUG | 10/02/2023 | 11/05/2023 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 202.79 | 137.89 | 68 | 20
8 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Laying of Additional pipe line for Augmentation of GHORADAHA water Supply Scheme under, Arambagh Sub Division,of Hooghly Division PHE Dte. (Khanakul - II Block) | Assistant Engineer | Junior Engineer (Civill) | ORD/000306/2024-2025 | 3662/HUG | 13/11/2024 | 10/08/2025 | M/S T.K.B. CONSTRUCTION | 79.95 | 0 | 0 | 50
9 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Construction of supporting arrangement for LDS and allied works of GHORADAHA Piped Water Supply Scheme under Arambag Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000060/2024-2025 | 2407/HUG | 26/06/2024 | 23/03/2025 | DILIP KUMAR GHOSH | 17.92 | 0 | 0 | 75
10 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Goradaha water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000212/2022-2023 | 839/ED | 14/02/2023 | 01/06/2025 | M/S S R ENTERPRISE | 21.49 | 11.63 | 54.13 | 15
Total | [13 empty] | 528.12 | 263.78 | 49.95