## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Preparation of DPR for Augmentation of Ghoradaha Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000100/2022-2023 | 390/Arg | 31/05/2022 | 30/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 3.34 | 79.17 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 1385/21/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.81 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1234/10/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 17.59 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Quotation for New Service Connection of Goradaha w/s Scheme,TW No-3 Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte |  |  | BILL/03627/2023-2024 | 220 | 25/08/2023 | 25/08/2023 | WBSEDCL | 6.53 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Quotation Bill for New Service Connection at |  |  | BILL/04140/2023-2024 | 390 | 02/11/2023 | 02/11/2023 | WBSEDCL | 8.75 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme with Construction of Boundary wall at 1st T.W Site, Repairing of Switch room, Laying of Rising main with necessary interconnection with T.W. & Distribution System & Functional Household tap Connection under Arambag SUb-Division of Hooghly Division, PHE Dte. within Khanakul -II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000716/2022-2023 | 493/HUG | 20/02/2023 | 21/05/2023 | DILIP KUMAR GHOSH | 149.07 | 110.91 | 74.4 | 25
7 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme by Sinking of 2 Nos. Tube well, Laying Distribution System, Construction of 2 Nos. Switch Room at 3rd & 4th Tubewell site and Boundary wall at 2nd, 3rd & 4th Tubewell site under Arambag Sub-Division of Hooghly Division PHE Dte. within Khanakul - II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000702/2022-2023 | 396/HUG | 10/02/2023 | 11/05/2023 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 202.79 | 137.89 | 68 | 20
8 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Laying of Additional pipe line for Augmentation of GHORADAHA water Supply Scheme under, Arambagh Sub Division,of Hooghly Division PHE Dte. (Khanakul - II Block) | Assistant Engineer | Junior Engineer (Civill) | ORD/000306/2024-2025 | 3662/HUG | 13/11/2024 | 10/08/2025 | M/S T.K.B. CONSTRUCTION | 79.95 | 0 | 0 | 50
9 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Construction of supporting arrangement for LDS and allied works of GHORADAHA Piped Water Supply Scheme under Arambag Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000060/2024-2025 | 2407/HUG | 26/06/2024 | 23/03/2025 | DILIP KUMAR GHOSH | 17.92 | 0 | 0 | 75
10 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Goradaha water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000212/2022-2023 | 839/ED | 14/02/2023 | 01/06/2025 | M/S S R ENTERPRISE | 21.49 | 11.63 | 54.13 | 15
11 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GHOSHPUR PWSS-5nos (2) GHORADAHA PWSS-4nos (3) KAKNAN PWSS-3nos (4) BHANGAMORA PWSS-2nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002650/2024-2025 | 817/Arg | 23/08/2024 | 22/09/2024 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 529.1 | 263.78 | 49.85