## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamalpur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000149/2022-2023 | 3492/ED | 30/12/2022 | 30/03/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.6 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01121/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 97.65 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | Material Requisition To Resource Division |  |  | RTOR000528/2023-2024 | 3059/35/Hug | 11/10/2023 |  | Resource Division | 22.49 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-II |  |  | BILL/06044/2023-2024 | 743 | 08/02/2024 |  | WBSEDCL | 3.68 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-I |  |  | BILL/06045/2023-2024 | 744 | 08/02/2024 |  | WBSEDCL | 14.44 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-I |  |  | BILL/06045/2023-2024 | 744 | 08/02/2024 |  | WBSEDCL | 14.44 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | Durgapur PH__II Water supply Scheme |  |  | BILL/00456/2024-2025 | null | 14/05/2024 |  | WBSEDCL | 3.68 | 0 | 0 | null
8 | HOOGHLY | Dhaniakhali | Hooghly Division | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12229 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 16/08/2024 | S. P. CONSTRUCTION | 5872.33 | 125.26 | 2.13 | 30
Total | [13 empty] | 6051.31 | 125.26 | 2.07