## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Material Requisition To Resource Division |  |  | RTOR000450/2023-2024 | 3057/24/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 10.79 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Material Requisition To Resource Division |  |  | RTOR000227/2022-2023 | 127/33/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 40.69 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | KELEPARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000262/2023-2024 | 2236/HUG | 01/08/2023 | 27/04/2024 | M/S R K ENTERPRISE | 502.36 | 87.56 | 17.43 | 10
4 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KELEPARA PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000164/2024-2025 | 1188/ED | 14/06/2024 | 12/09/2024 | PADMA ENGINEERING CO. | 10.74 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Electric quot. of WBSEDCL for New service Connection of Kelepara T/W-II W/S scheme under Electrical Division PHE Dte. (SM/12232) |  |  | BILL/01616/2024-2025 | 375 | 12/08/2024 | 12/08/2024 | WBSEDCL | 3.67 | 0 | 0 | 0
6 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kelepara water supply scheme, T.W. No.- I & II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1,Junior Engineer3 | ORD/000158/2022-2023 | 3494/ED | 30/12/2022 | 17/06/2025 | PADMA ENGINEERING CO. | 20.47 | 0 | 0 | 30
7 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Laying Distribution main by HDD process with HDPE pipe at Mayapur Z1, Kelepara, Krishnanagar Z1 & Z2 W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000228/2024-2025 | 3438/HUG | 03/10/2024 | 28/09/2025 | MS PRADIP KUMAR PAL | 15.93 | 0 | 0 | 40
8 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GHOLDGRUI PWSS(Z-II)- 3no¿s, (2) KELEPARA PWSS- 2 no¿s, (3) RASULPUR PWSS- 5 no¿s, (4) BHANGAMORA PWSS- 1 no¿s, (5) SHYAMPUR PWSS(Z-III)- 2 no¿s, (6) GOPALDAHA PWSS- 1 no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002302/2024-2025 | 1156/Arg | 10/12/2024 | 10/01/2025 | KARALI MOHAN KHAMRUI | 0.98 | 0 | 0 | 99
Total | [13 empty] | 605.63 | 87.56 | 14.46