## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Material Requisition To Resource Division |  |  | RTOR000450/2023-2024 | 3057/24/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 10.79 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Material Requisition To Resource Division |  |  | RTOR000227/2022-2023 | 127/33/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 40.69 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | KELEPARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000262/2023-2024 | 2236/HUG | 01/08/2023 | 27/04/2024 | M/S R K ENTERPRISE | 502.36 | 87.56 | 17.43 | 10
4 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KELEPARA PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000164/2024-2025 | 1188/ED | 14/06/2024 | 12/09/2024 | PADMA ENGINEERING CO. | 10.74 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Electric quot. of WBSEDCL for New service Connection of Kelepara T/W-II W/S scheme under Electrical Division PHE Dte. (SM/12232) |  |  | BILL/01616/2024-2025 | 375 | 12/08/2024 | 12/08/2024 | WBSEDCL | 3.67 | 0 | 0 | 0
6 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kelepara water supply scheme, T.W. No.- I & II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1,Junior Engineer3 | ORD/000158/2022-2023 | 3494/ED | 30/12/2022 | 17/06/2025 | PADMA ENGINEERING CO. | 20.47 | 0 | 0 | 30
7 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12232 | New | Laying Distribution main by HDD process with HDPE pipe at Mayapur Z1, Kelepara, Krishnanagar Z1 & Z2 W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000228/2024-2025 | 3438/HUG | 03/10/2024 | 28/09/2025 | MS PRADIP KUMAR PAL | 15.93 | 0 | 0 | 40
Total | [13 empty] | 604.65 | 87.56 | 14.48