## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Routhkhana water supply scheme, T.W. No.- I & II, Block: Khanakul-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000169/2022-2023 | 3502/ED | 30/12/2022 | 30/03/2023 | BINAPANI ENTERPRISE | 21.48 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 01/04/2026 | MACKINTOSH BURN LIMITED | 5743.06 | 369.63 | 6.44 | 50
3 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 1385/11/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 15.88 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Material Requisition To Resource Division |  |  | RTOR000402/2023-2024 | 3057/50/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.88 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1234/42/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 48.75 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ROUTHKHANA PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000149/2024-2025 | 1172/ED | 14/06/2024 | 12/09/2024 | BINAPANI ENTERPRISE | 10.64 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-I, CHINRA (Z-I AND II), ROUTHKHANA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000841/2023-2024 | 721/HUG | 05/03/2024 | 27/08/2025 | SPG ENTERPRISES | 64.23 | 0 | 0 | 50
8 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987362 Reference Id-503547192 |  |  | BILL/06057/2023-2024 | 760 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.26 | 0 | 0 | 0
9 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987354 Reference Id-503547191 |  |  | BILL/06058/2023-2024 | 758 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.85 | 0 | 0 | 0
10 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 01/01/2026 | TECHVISION | 14.8 | 0 | 0 | 20
Total | [13 empty] | 5942.83 | 369.63 | 6.22