## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Routhkhana water supply scheme, T.W. No.- I & II, Block: Khanakul-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000169/2022-2023 | 3502/ED | 30/12/2022 | 30/03/2023 | BINAPANI ENTERPRISE | 21.48 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 1385/11/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 15.88 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Material Requisition To Resource Division |  |  | RTOR000402/2023-2024 | 3057/50/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.88 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1234/42/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 48.75 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ROUTHKHANA PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000149/2024-2025 | 1172/ED | 14/06/2024 | 12/09/2024 | BINAPANI ENTERPRISE | 10.64 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987362 Reference Id-503547192 |  |  | BILL/06057/2023-2024 | 760 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.26 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987354 Reference Id-503547191 |  |  | BILL/06058/2023-2024 | 758 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.85 | 0 | 0 | 0
8 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12233 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-I, CHINRA (Z-I AND II), ROUTHKHANA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000841/2023-2024 | 721/HUG | 05/03/2024 | 27/08/2025 | SPG ENTERPRISES | 64.23 | 0 | 0 | 50
Total | [13 empty] | 184.97 | 0 | 0