## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 1385/51/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.76 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Material Requisition To Resource Division |  |  | RTOR000468/2023-2024 | 3057/16/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.76 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1234/41/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 47.19 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000171/2024-2025 | 3170/HUG | 10/09/2024 | 25/10/2024 | BIMAL KUMAR HALDER | 48.47 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte |  |  | ORD/000405/2024-2025 | 3782/HUG | 25/11/2024 | 24/01/2025 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NATIBPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000167/2024-2025 | 1190/ED | 14/06/2024 | 12/09/2024 | BARMAN ROY TRADERS | 10.47 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Quotation Money depostion for new service connection at Natibpur pwss, P.H No-I, Dist- Hooghly uned ED, PHED. App. No.-5004020953 SM/12235 |  |  | BILL/02301/2024-2025 | BP-24-25-598 | 21/11/2024 | 21/11/2024 | WBSEDCL | 8.56 | 0 | 0 | 0
8 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Quotation money deposition for new service connection at Natibpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004216541 Reference ID- 503658560 SM Code-12235 |  |  | BILL/01652/2024-2025 | 410 | 21/08/2024 | 21/08/2024 | WBSEDCL | 7.79 | 0 | 0 | 0
9 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/12235 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Natibpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer4 | ORD/000089/2022-2023 | 3471/ED | 30/12/2022 | 30/06/2025 | BARMAN ROY TRADERS | 21.9 | 0 | 0 | 40
Total | [13 empty] | 239.02 | 0 | 0