## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I | Hooghly Division | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | SM/12239 | New | Material Requisition To Resource Division |  |  | RTOR000480/2023-2024 | 3060/17/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.96 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-I | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | SM/12239 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000164/2022-2023 | 3498/ED | 30/12/2022 | 30/03/2023 | ANJAN ENTERPRISE | 21.33 | 0 | 0 | 30
3 | HOOGHLY | Chanditala-I | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | SM/12239 | New | Quotation money deposition for new service connection at Nababpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004064410 Reference ID- 503597307 SM Code- 12239 |  |  | BILL/02122/2024-2025 | 560 | 11/11/2024 | 11/11/2024 | WBSEDCL | 4.18 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-I | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | SM/12239 | New | Quotation bill for new service connection charges at Nababpur PWSS P.H. No.-I, Hooghly. Application No. 5004064466 Ref ID: 503597309 |  |  | BILL/00035/2024-2025 | 21 | 05/04/2024 | 05/04/2024 | WBSEDCL | 4.1 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-I | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | SM/12239 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000193/2022-2023 | 786/ED | 09/02/2023 | 05/02/2025 | M/S P.P. ELECTRICALS | 22.36 | 0 | 0 | 50
6 | HOOGHLY | Chanditala-I | Hooghly Division | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | SM/12239 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 10/08/2025 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 0 | 0 | 9
Total | [13 empty] | 3309.15 | 0 | 0