## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Material Requisition To Resource Division |  |  | RTOR000309/2023-2024 | 1384/6/Hug | 16/05/2023 | 16/05/2023 | Resource Division | 2.91 | 0 | 0 | 0
2 | HOOGHLY | Jangipara | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Material Requisition To Resource Division |  |  | RTOR000496/2023-2024 | 3060/16/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 2.91 | 0 | 0 | 0
3 | HOOGHLY | Jangipara | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Material Requisition To Resource Division |  |  | RTOR000173/2022-2023 | 792/2/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 2.91 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Bishnupur water supply scheme,PH No-II |  |  | BILL/02310/2023-2024 | 144 | 26/07/2023 | 26/07/2023 | WBSEDCL | 2.89 | 0 | 0 | 0
5 | HOOGHLY | Jangipara | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Bishnupur water supply scheme, P H No -I |  |  | BILL/02286/2023-2024 | 141 | 25/07/2023 | 25/07/2023 | WBSEDCL | 3.39 | 0 | 0 | 0
6 | HOOGHLY | Jangipara | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | BISHNUPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Jangipara Block Junior Engineer (Civill),Junior Engineer (Civill) | ORD/000775/2022-2023 | 749/Hug | 15/03/2023 | 02/04/2025 | TOTON MONDAL | 232.56 | 158.88 | 68.32 | 92
7 | HOOGHLY | Jangipara | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000224/2024-2025 | 1196/ED | 14/06/2024 | 01/07/2025 | PURUSHOTTAM ENTERPRISE | 10.75 | 0 | 0 | 100
8 | HOOGHLY | Jangipara | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000172/2024-2025 | 1195/ED | 14/06/2024 | 21/05/2026 | MAA KALI ENTERPRISE | 10.7 | 0 | 0 | 40
9 | HOOGHLY | Jangipara | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | SM/12242 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bishnupur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000138/2022-2023 | 3486/ED | 30/12/2022 | 25/05/2026 | BARMAN ROY TRADERS | 20.46 | 19.87 | 97.11 | 85
Total | [13 empty] | 289.47 | 178.75 | 61.75