## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12243 | New | Material Requisition To Resource Division |  |  | RTOR000240/2023-2024 | 1386/19/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 12.09 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12243 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 1264/20/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 16.64 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12243 | New | Material Requisition To Resource Division |  |  | RTOR000512/2023-2024 | 3059/11/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 3.18 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12243 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Durgapur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000146/2022-2023 | 3489/ED | 30/12/2022 | 30/03/2023 | M/S CHANDIMATA ELECTRICALS | 20.38 | 11.23 | 55.1 | 35
5 | HOOGHLY | Dhaniakhali | Electrical | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12243 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-I |  |  | BILL/05129/2023-2024 | 693 | 22/01/2024 | 22/01/2024 | WBSEDCL | 11.8 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Electrical | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12243 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-II |  |  | BILL/05131/2023-2024 | 694 | 22/01/2024 | 22/01/2024 | WBSEDCL | 5.69 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12243 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/04/2026 | S. P. CONSTRUCTION | 5872.33 | 212.01 | 3.61 | 30
Total | [13 empty] | 5942.12 | 223.24 | 3.76