## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I | Electrical | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12245 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dudhkalmi water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000144/2022-2023 | 3488/ED | 30/12/2022 | 30/03/2023 | S.P. CONSTRUCTION | 21.37 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-I | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12245 | New | Material Requisition To Resource Division |  |  | RTOR000319/2023-2024 | 1384/16/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 16.88 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-I | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12245 | New | Material Requisition To Resource Division |  |  | RTOR000524/2023-2024 | 3060/15/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 16.88 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-I | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12245 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1236/1/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 28.77 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-I | Electrical | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12245 | New | Dudhkalmi w/s scheme,P H No 1 |  |  | BILL/04509/2023-2024 | 559 | 21/12/2023 | 21/12/2023 | WBSEDCL | 5.64 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-I | Electrical | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12245 | New | Quotation bill for new service connection charges at Dudhkalmi PWSS P.H. No.-II, Hooghly. Application No. 5004031077 Ref ID: 503576014 |  |  | BILL/00039/2024-2025 | 24 | 05/04/2024 | 05/04/2024 | WBSEDCL | 5.3 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-I | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12245 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 10/08/2025 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 0 | 0 | 9
Total | [13 empty] | 3338.07 | 0 | 0