## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Material Requisition To Resource Division |  |  | RTOR000304/2023-2024 | 1384/1/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 18.08 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-I | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Material Requisition To Resource Division |  |  | RTOR000378/2023-2024 | 3005/20/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 5.56 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-I | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Material Requisition To Resource Division |  |  | RTOR000490/2023-2024 | 3060/14/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 18.08 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-I | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Material Requisition To Resource Division |  |  | RTOR000163/2022-2023 | 79/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 4.95 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-I | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandhpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000128/2022-2023 | 3482/ED | 30/12/2022 | 30/03/2023 | ASHUTOSH DAS & CO. | 21.38 | 0 | 0 | 90
6 | HOOGHLY | Chanditala-I | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-I |  |  | BILL/04445/2023-2024 | 506 | 08/12/2023 | 08/12/2023 | WBSEDCL | 0.4 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-I | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-II |  |  | BILL/04446/2023-2024 | 507 | 08/12/2023 | 08/12/2023 | WBSEDCL | 12.9 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-I | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | PAYMENT TO ROAD RESTORATION TO PWD BANDPUR ICHAPASARA ROAD |  |  | BILL/00683/2024-2025 | BP-2024-25-500 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 8.03 | 0 | 0 | 0
9 | HOOGHLY | Chanditala-I | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12248 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BANDHPUR water supply scheme, TW No. III, Block: Chanditala-I, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003084/2024-2025 | 479/ED | 18/03/2025 | 16/06/2025 | S.K. ENTERPRISE | 11.3 | 0 | 0 | 0
Total | [13 empty] | 100.69 | 0 | 0