## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathpur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000148/2022-2023 | 3491/ED | 30/12/2022 | 26/04/2025 | BISALAXMI ENTERPRISE | 20.31 | 17.69 | 87.08 | 50
2 | HOOGHLY | Jangipara | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | JAGANNATHPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000263/2023-2024 | 2237/HUG | 01/08/2023 | 30/01/2025 | SIBSANKAR CHOWDHURY | 584.82 | 224.7 | 38.42 | 40
3 | HOOGHLY | Jangipara | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Material Requisition To Resource Division |  |  | RTOR000314/2023-2024 | 1384/11/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 13.26 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Material Requisition To Resource Division |  |  | RTOR000505/2023-2024 | 3060/18/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.26 | 0 | 0 | 0
5 | HOOGHLY | Jangipara | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Material Requisition To Resource Division |  |  | RTOR000171/2022-2023 | 79/5/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 13.26 | 0 | 0 | 0
6 | HOOGHLY | Jangipara | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JAGANNATHPUR HW SITE AND 2ND SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000139/2024-2025 | 427/SER | 31/07/2024 | 15/08/2024 | SUNITI MAIRA | 0.68 | 0.66 | 97.1 | 95
7 | HOOGHLY | Jangipara | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Quotation Bill for Suplimentary Quotation for NSC Jagannathpur W/S. Sch PH-I |  |  | BILL/05298/2023-2024 | 695 | 22/01/2024 | 22/01/2024 | WBSEDCL | 0.06 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Quotation Bill for New Service Connection at Jagannathpur W/S. Sch.PH-II |  |  | BILL/04609/2023-2024 | 607 | 04/01/2024 | 04/01/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
9 | HOOGHLY | Jangipara | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Quotation Bill for New Service Connection at Jagganathpur W/S. Sch. PH-I |  |  | BILL/04639/2023-2024 | 621 | 08/01/2024 | 08/01/2024 | WBSEDCL | 6.73 | 0 | 0 | 0
10 | HOOGHLY | Jangipara | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | SM/12249 | New | Quotation for New service connection at Jagannathpur W/S. Sch. |  |  | BILL/06221/2023-2024 | 825 | 01/03/2024 | 01/03/2024 | WBSEDCL | 10.23 | 0 | 0 | 0
Total | [13 empty] | 665.97 | 243.04 | 36.49