## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000147/2022-2023 | 3490/ED | 30/12/2022 | 30/03/2023 | P.K. ENGINEERING | 20.24 | 9.82 | 48.53 | 49
2 | HOOGHLY | Chanditala-I | Hooghly Division | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | Material Requisition To Resource Division |  |  | RTOR000507/2023-2024 | 3060/13/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.5 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-I | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-II |  |  | BILL/04444/2023-2024 | 508 | 08/12/2023 | 08/12/2023 | WBSEDCL | 9.7 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-I | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-I |  |  | BILL/04443/2023-2024 | 501 | 08/12/2023 | 08/12/2023 | WBSEDCL | 3.77 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-I | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000192/2022-2023 | 785/ED | 09/02/2023 | 10/05/2023 | SRI KRISHNA NIRMAN | 20.26 | 14.03 | 69.25 | 65
6 | HOOGHLY | Chanditala-I | Hooghly Division | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT HARIPUR HW SITE AND 2ND SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000138/2024-2025 | 426/SER | 31/07/2024 | 15/08/2024 | SUNITI MAIRA | 0.68 | 0.66 | 97.09 | 95
7 | HOOGHLY | Chanditala-I | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | Quotation money deposition for new service connection at Haripur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 100000123497 Reference ID- 860318447 SM Code- 12250 |  |  | BILL/02303/2024-2025 | BP-24-25-597 | 21/11/2024 | 21/11/2024 | WBSEDCL | 2.22 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-I | Hooghly Division | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | SM/12250 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 10/08/2025 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 283.99 | 8.76 | 9
Total | [13 empty] | 3312.59 | 308.5 | 9.31