## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12251 | New | Material Requisition To Resource Division |  |  | RTOR000529/2023-2024 | 3059/7/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.89 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12251 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1264/11/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 24.6 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Electrical | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12251 | New | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-II |  |  | BILL/05715/2023-2024 | 704 | 25/01/2024 | 25/01/2024 | WBSEDCL | 5.78 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12251 | New | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-I |  |  | BILL/05718/2023-2024 | 705 | 25/01/2024 | 25/01/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Hooghly Division | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12251 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/04/2026 | S. P. CONSTRUCTION | 5872.33 | 0 | 0 | 30
Total | [13 empty] | 5921.14 | 0 | 0