## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12252 | New | Material Requisition To Resource Division |  |  | RTOR000261/2023-2024 | 1386/40/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 10.44 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12252 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1264/17/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 19.8 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12252 | New | Material Requisition To Resource Division |  |  | RTOR000513/2023-2024 | 3059/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 2.16 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12252 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chautara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000080/2022-2023 | 3462/ED | 30/12/2022 | 30/03/2023 | DAS ENTERPRISE | 20.46 | 16.79 | 82.09 | 35
5 | HOOGHLY | Dhaniakhali | Electrical | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12252 | New | Electric quot. of WBSEDCL for New Connection of Choutara T/W-I W/S scheme under ED PHE Dte. (SM/12252) |  |  | BILL/06544/2023-2024 | 909 | 21/03/2024 | 21/03/2024 | WBSEDCL | 3.43 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Electrical | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12252 | New | Electric quot. of WBSEDCL for New Connection of Choutara T/W-II W/S scheme under ED PHE Dte. (SM/12252) |  |  | BILL/06548/2023-2024 | 908 | 21/03/2024 | 21/03/2024 | WBSEDCL | 3.41 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12252 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/09/2025 | S. P. CONSTRUCTION | 5872.33 | 130.33 | 2.22 | 30
Total | [13 empty] | 5932.02 | 147.12 | 2.48