## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12253 | New | Material Requisition To Resource Division |  |  | RTOR000226/2023-2024 | 1386/5/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 11.59 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12253 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1264/18/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 15.5 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Electrical | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12253 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kanajoli water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000156/2022-2023 | 3493/ED | 30/12/2022 | 30/03/2023 | CHATTERJEE BROTHERS | 20.25 | 0 | 0 | 35
4 | HOOGHLY | Dhaniakhali | Electrical | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12253 | New | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-I |  |  | BILL/05060/2023-2024 | 685 | 19/01/2024 | 19/01/2024 | WBSEDCL | 11.72 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12253 | New | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-II |  |  | BILL/05061/2023-2024 | 684 | 19/01/2024 | 19/01/2024 | WBSEDCL | 4.03 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Hooghly Division | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12253 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/04/2026 | S. P. CONSTRUCTION | 5872.33 | 0 | 0 | 30
Total | [13 empty] | 5935.42 | 0 | 0