## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gurbari water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000082/2022-2023 | 3464/ED | 30/12/2022 | 30/03/2023 | A.G. ENTERPRISE | 21.58 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 1264/23/HUG | 03/05/2023 |  | Resource Division | 12.17 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Material Requisition To Resource Division |  |  | RTOR000266/2023-2024 | 1386/45/Hug | 15/05/2023 |  | Resource Division | 17.02 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for GURBARI Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000335/2023-2024 | 2422/HUG | 11/08/2023 | 09/11/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 51.96 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01117/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 94.34 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Material Requisition To Resource Division |  |  | RTOR000521/2023-2024 | 3059/38/Hug | 11/10/2023 |  | Resource Division | 17.02 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Electrical | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Quotation Bill for New Service Connection at Gurbari W/S. Sch. TW-I |  |  | BILL/05065/2023-2024 | 681 | 19/01/2024 |  | WBSEDCL | 3.25 | 0 | 0 | 0
8 | HOOGHLY | Dhaniakhali | Electrical | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Quotation Bill for New Service Connection at Gurbari W/S. Sch. TW-I |  |  | BILL/05065/2023-2024 | 681 | 19/01/2024 |  | WBSEDCL | 3.25 | 0 | 0 | 0
9 | HOOGHLY | Dhaniakhali | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 12/05/2024 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 20.03 | 0.89 | 20
10 | HOOGHLY | Dhaniakhali | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12254 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000325/2023-2024 | 2408/HUG | 11/08/2023 | 25/09/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 6.61 | 8.1 | 20
Total | [13 empty] | 2558.1 | 26.64 | 1.04