## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Polba-Dadpur | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000084/2022-2023 | 3466/ED | 30/12/2022 | 30/03/2023 | T.N. BANERJEE | 21.6 | 0 | 0 | 0
2 | HOOGHLY | Polba-Dadpur | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 1386/41/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.37 | 0 | 0 | 0
3 | HOOGHLY | Polba-Dadpur | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 1264/4/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 17.97 | 0 | 0 | 0
4 | HOOGHLY | Polba-Dadpur | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Material Requisition To Resource Division |  |  | RTOR000516/2023-2024 | 3059/41/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.37 | 0 | 0 | 0
5 | HOOGHLY | Polba-Dadpur | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Quotation for new service connection at Hasnan W/S Sch., T/W No. - I, Block - Polba-Dadpur, Dist. - Hooghly |  |  | BILL/03712/2023-2024 | 255 | 05/09/2023 | 05/09/2023 | WBSEDCL | 12.17 | 0 | 0 | 0
6 | HOOGHLY | Polba-Dadpur | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Road Restoration |  |  | BILL/00685/2023-2024 | BP-2023-24-529 | 17/10/2023 | 17/10/2023 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 12 | 0 | 0 | 0
7 | HOOGHLY | Polba-Dadpur | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Quotation for new service connection at Hasnan W/S Sch. , T/W No - II, Block- Polba-Dadpur, Dist - Hooghly |  |  | BILL/03713/2023-2024 | 254 | 05/09/2023 | 05/09/2023 | WBSEDCL | 4.01 | 0 | 0 | 0
8 | HOOGHLY | Polba-Dadpur | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/002464/2023-2024 | 325/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 20.85 | 0 | 0 | 0
9 | HOOGHLY | Polba-Dadpur | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | SM/12255 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000811/2022-2023 | 955/HUG | 30/03/2023 | 02/09/2025 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 436.06 | 11.87 | 15
Total | [13 empty] | 3799.42 | 436.06 | 11.48