## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Material Requisition To Resource Division |  |  | RTOR000267/2023-2024 | 1386/46/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.93 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Material Requisition To Resource Division |  |  | RTOR000523/2023-2024 | 3059/37/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.93 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 1264/14/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 42.75 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Lokabati PH__II Water supply Scheme |  |  | BILL/05987/2023-2024 | 724 | 05/02/2024 | 05/02/2024 | WBSEDCL | 17.53 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Lokabati PH__I Water supply Scheme |  |  | BILL/05988/2023-2024 | 725 | 05/02/2024 | 05/02/2024 | WBSEDCL | 4.7 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/04/2026 | S. P. CONSTRUCTION | 5872.33 | 371.19 | 6.32 | 30
7 | HOOGHLY | Dhaniakhali | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Lokabati water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000087/2022-2023 | 3469/ED | 30/12/2022 | 01/08/2025 | INDRANI ENTERPRISE | 22.4 | 0 | 0 | 75
8 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-III) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002233/2024-2025 | 407/CH | 10/03/2025 | 05/03/2026 | TECHVISION | 4.2 | 0 | 0 | 79
Total | [13 empty] | 6003.76 | 371.19 | 6.18