## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Material Requisition To Resource Division |  |  | RTOR000267/2023-2024 | 1386/46/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.93 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Material Requisition To Resource Division |  |  | RTOR000523/2023-2024 | 3059/37/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.93 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 1264/14/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 42.75 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Lokabati PH__II Water supply Scheme |  |  | BILL/05987/2023-2024 | 724 | 05/02/2024 | 05/02/2024 | WBSEDCL | 17.53 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Lokabati PH__I Water supply Scheme |  |  | BILL/05988/2023-2024 | 725 | 05/02/2024 | 05/02/2024 | WBSEDCL | 4.7 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/04/2026 | S. P. CONSTRUCTION | 5872.33 | 0 | 0 | 30
7 | HOOGHLY | Dhaniakhali | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12256 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Lokabati water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000087/2022-2023 | 3469/ED | 30/12/2022 | 01/08/2025 | INDRANI ENTERPRISE | 22.4 | 0 | 0 | 75
Total | [13 empty] | 5999.56 | 0 | 0