## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chalua water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000079/2022-2023 | 3461/ED | 30/12/2022 | 30/03/2023 | M/S P.P. ELECTRICALS | 22.94 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | Material Requisition To Resource Division |  |  | RTOR000249/2023-2024 | 1386/28/Hug | 15/05/2023 |  | Resource Division | 22.55 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01117/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 94.34 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Hooghly Division | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | Material Requisition To Resource Division |  |  | RTOR000531/2023-2024 | 3059/6/Hug | 11/10/2023 |  | Resource Division | 22.55 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | Quotation of New Service Connection for Chalua w/s Scheme,TW No-I,Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte.(SM/12257) Application No-5003977900 Reference Id-503540601 |  |  | BILL/06104/2023-2024 | 764 | 16/02/2024 |  | WBSEDCL | 4.74 | 0 | 0 | null
6 | HOOGHLY | Dhaniakhali | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | Quotation of New Service Connection for Chalua w/s Scheme,PH No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12257) Application No-5003977943 Reference Id-503540606 |  |  | BILL/06103/2023-2024 | 763 | 16/02/2024 |  | WBSEDCL | 6.68 | 0 | 0 | null
7 | HOOGHLY | Dhaniakhali | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | Quotation of New Service Connection for Chalua w/s Scheme,PH No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12257) Application No-5003977943 Reference Id-503540606 |  |  | BILL/06103/2023-2024 | 763 | 16/02/2024 |  | WBSEDCL | 6.68 | 0 | 0 | null
8 | HOOGHLY | Dhaniakhali | Hooghly Division | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12257 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 16/08/2024 | S. P. CONSTRUCTION | 5872.33 | 0 | 0 | 30
Total | [13 empty] | 6052.8 | 0 | 0