## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12260 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Simla water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000120/2022-2023 | 3476/ED | 30/12/2022 | 30/03/2023 | A.S. ENTERPRISE | 21.42 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12260 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01117/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 94.34 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12260 | New | Material Requisition To Resource Division |  |  | RTOR000486/2023-2024 | 3059/21/Hug | 11/10/2023 |  | Resource Division | 18.29 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12260 | New | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-I |  |  | BILL/05321/2023-2024 | 696 | 22/01/2024 |  | WBSEDCL | 6.37 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12260 | New | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-I |  |  | BILL/05321/2023-2024 | 696 | 22/01/2024 |  | WBSEDCL | 6.37 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12260 | New | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-II |  |  | BILL/05334/2023-2024 | 697 | 22/01/2024 |  | WBSEDCL | 5.91 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Hooghly Division | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12260 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 16/08/2024 | S. P. CONSTRUCTION | 5872.33 | 135.71 | 2.31 | 30
Total | [13 empty] | 6025.01 | 135.71 | 2.25