## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 1386/20/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 15.66 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | Material Requisition To Resource Division |  |  | RTOR000515/2023-2024 | 3059/10/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.66 | 0 | 0 | 0
3 | HOOGHLY | Dhaniakhali | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 1264/15/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 32.44 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Electrical | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-II |  |  | BILL/05066/2023-2024 | 680 | 19/01/2024 | 19/01/2024 | WBSEDCL | 3.89 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-I |  |  | BILL/05713/2023-2024 | 706 | 25/01/2024 | 25/01/2024 | WBSEDCL | 4.32 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | ROAD RESTORATION PAYMENT TO PWD FOR BHASTARA MAJINAN ROAD |  |  | BILL/00669/2024-2025 | 1234 | 27/09/2024 | 27/09/2024 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 17.55 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/04/2026 | S. P. CONSTRUCTION | 5872.33 | 0 | 0 | 30
8 | HOOGHLY | Dhaniakhali | Electrical | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12262 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khajurdaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000159/2022-2023 | 3495/ED | 30/12/2022 | 03/04/2027 | AHALYA ENGINEERING WORKS | 20.35 | 0 | 0 | 40
Total | [13 empty] | 5982.2 | 0 | 0