## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bishnupur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000131/2022-2023 | 3485/ED | 30/12/2022 | 01/09/2025 | C.M.S. ENGINEERING CONCERN | 22.86 | 20.79 | 90.95 | 45
2 | HOOGHLY | Dhaniakhali | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2023-2024 | 2066/HUG | 17/07/2023 | 02/08/2025 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 275.85 | 12.23 | 20
3 | HOOGHLY | Dhaniakhali | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Laying of Rising main with necessary interconnection with T.W., OHR & DistributionSystem ,Construction of switch-rooms & boundary walls at different TW site for Bishnupur Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:-Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000330/2023-2024 | 2415/HUG | 11/08/2023 | 22/03/2025 | GEE BEE NIRMAN CO PRIVATE LIMITED | 54.65 | 8.62 | 15.77 | 30
4 | HOOGHLY | Dhaniakhali | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BISHNUPUR, DASHGHARA ZONE-I, DASHGHARA ZONE-II (1NO.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000323/2023-2024 | 2407/HUG | 11/08/2023 | 25/09/2023 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 26.42 | 32.36 | 40
5 | HOOGHLY | Dhaniakhali | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Material Requisition To Resource Division |  |  | RTOR000269/2023-2024 | 1386/48/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.19 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Material Requisition To Resource Division |  |  | RTOR000525/2023-2024 | 3059/36/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.19 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Construction of Store room for temporary Chlorine and maintenance material storage For Dasghara Zone-I, Bishnupur and Shrirampur Piped Water Supply under Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001034/2023-2024 | 277/CH | 14/03/2024 | 21/03/2024 | M/S BIMAL DAS AND CO. | 0.95 | 0.95 | 99.65 | 100
8 | HOOGHLY | Dhaniakhali | Electrical | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Bishnupur PH__I Water supply Scheme |  |  | BILL/05986/2023-2024 | 723 | 05/02/2024 | 05/02/2024 | WBSEDCL | 7.9 | 0 | 0 | 0
9 | HOOGHLY | Dhaniakhali | Electrical | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12263 | New | Quotation of New service Connection Charge for Bishnupur w/s Scheme,TW No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12263) Application no-5003995286 Reference Id-503552526 |  |  | BILL/06105/2023-2024 | 762 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
Total | [13 empty] | 2466.15 | 332.62 | 13.49