## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kumrul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000086/2022-2023 | 3468/ED | 30/12/2022 | 30/03/2023 | DEY ENTERPRISE | 23.33 | 0 | 0 | 0
2 | HOOGHLY | Dhaniakhali | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/04/2026 | S. P. CONSTRUCTION | 5872.33 | 359.37 | 6.12 | 30
3 | HOOGHLY | Dhaniakhali | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Material Requisition To Resource Division |  |  | RTOR000251/2023-2024 | 1386/30/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 26.93 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Material Requisition To Resource Division |  |  | RTOR000360/2023-2024 | 3004/21/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 17.29 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Material Requisition To Resource Division |  |  | RTOR000536/2023-2024 | 3059/3/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 26.93 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. CAR NO.- WB-04G-2822 | Assistant Engineer 1 | Junior Engineer1,Junior Engineer2 | ORD/003411/2023-2024 | 139_AE-I/ED | 29/01/2024 | 28/06/2024 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.14 | 19.87 | 0
7 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer5 | ORD/002502/2023-2024 | 139/AE-I/ED | 29/01/2024 | 28/06/2024 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.43 | 59.6 | 5
8 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer1,Junior Engineer2 | ORD/003308/2023-2024 | 139_/AE-I/ED | 29/01/2024 | 28/06/2024 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.15 | 20.53 | 0
9 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-I |  |  | BILL/05128/2023-2024 | 698 | 22/01/2024 | 22/01/2024 | WBSEDCL | 5.23 | 0 | 0 | 0
10 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Supply of diesel & mobile oil for inspection car of AE-I under ED , PHE Dte. |  |  | BILL/06465/2023-2024 | 891 | 18/03/2024 | 18/03/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
11 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 From 01/06/2024 to 30/06/2024 |  |  | BILL/01368/2024-2025 | 330 | 30/07/2024 | 30/07/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
12 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-II |  |  | BILL/05126/2023-2024 | 699 | 22/01/2024 | 22/01/2024 | WBSEDCL | 5.76 | 0 | 0 | 0
13 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2024 WB-04G-2822 |  |  | BILL/00460/2024-2025 | 145 | 22/05/2024 | 22/05/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
14 | HOOGHLY | Dhaniakhali | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12265 | New | Supply of diesel and mobile for inspection car of AE-I under Electrical Division PHE Dte. |  |  | BILL/00258/2024-2025 | 90 | 26/04/2024 | 26/04/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
Total | [13 empty] | 5980.91 | 360.09 | 6.02