## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 2471/3/Hug | 18/11/2022 | 18/11/2022 | Resource Division | 19.58 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 11/05/2023 | MS D.PALIT AND CO. | 62.24 | 0 | 0 | 100
3 | HOOGHLY | Singur | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No. III, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000873/2023-2024 | 3446/ED | 11/08/2023 | 09/11/2023 | BISALAXMI ENTERPRISE | 11.5 | 0 | 0 | 0
4 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Material Requisition To Resource Division |  |  | RTOR000191/2022-2023 | 109/1/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 55.09 | 0 | 0 | 0
5 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Material Requisition To Resource Division |  |  | RTOR000158/2022-2023 | 01/11/Hug | 02/01/2023 | 02/01/2023 | Resource Division | 19.58 | 0 | 0 | 0
6 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 1383/9/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 19.93 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Quotation for new service connection at Basubati W/S Sch, TW-I (Head Work site), Dist. Hooghly |  |  | BILL/01916/2023-2024 | 90 | 13/07/2023 | 13/07/2023 | WBSEDCL | 3.85 | 0 | 0 | 0
8 | HOOGHLY | Singur | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Quotation Bill for New Service Connection at Basubati W/S. Sch. TW-II |  |  | BILL/04512/2023-2024 | 553 | 21/12/2023 | 21/12/2023 | WBSEDCL | 2.59 | 0 | 0 | 0
9 | HOOGHLY | Singur | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000130/2022-2023 | 3484/ED | 30/12/2022 | 30/03/2023 | ASHUTOSH DAS & CO. | 23.01 | 0 | 0 | 90
10 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 06/08/2023 | OSMAN SEKH | 80.85 | 0 | 0 | 100
11 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Basubati PWSS, Purushottampur PWSS, Nawpara PWSS, Bighati Z-II PWSS, Shibrambati Z-I PWSS, Sinhal Pathan PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000975/2023-2024 | 303/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 100
12 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main& Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in BASUBATI Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000747/2022-2023 | 683/Hug | 10/03/2023 | 30/09/2025 | MINTU CHAKRABORTY | 618.81 | 0 | 0 | 70
13 | HOOGHLY | Singur | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME | SM/12365 | New | Sinking of 1no. additional tubewell with Construction of switch-room, Tubewell connection & Other works at BASUBATI Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/002477/2024-2025 | 670/HUG | 12/03/2025 | 10/06/2025 | MINTU CHAKRABORTY | 92.31 | 0 | 0 | 0
Total | [13 empty] | 1010.29 | 0 | 0