## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Horizontal road crossing by trenchless method & parallel shifting of distribution pipe line at Ghanashyampur, Kamarkundu, Bora telermore, Sheetpara -Borai Beside NH12 Within Kamarpukur & Barakamalpur PWSS, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000462/2022-2023 | 2523/HUG | 23/11/2022 | 23/12/2022 | SURAJIT SINGHA RAY | 25.39 | 25.37 | 99.93 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Laying of UPVC pipe for crossing through culvert below National Highway - 2 including repairing of damage AC pipe for providing water supply at BORAI under BoraKamalpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000617/2022-2023 | 214/chan | 13/04/2022 | 28/04/2022 | G.K ENTERPRISE (GOUR KUMAR DAS) | 1.7 | 1.7 | 99.77 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Route survey Design drawing & DPR preparation of Barakamalpur Zone- I & II PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000171/2022-2023 | 266/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.98 | 4.98 | 99.96 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Route survey Design drawing & DPR preparation of Barakamalpur Zone- III & IV PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000173/2022-2023 | 267/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.71 | 4.69 | 99.55 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2022-2023 | 2686/12/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.33 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | AUGMENTATION of BARAKAMALPUR (ZONE-IV) Piped Water Supply Scheme with LDS, FHTC, Sinking of Tube Well & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000789/2022-2023 | 889/HUG | 27/03/2023 | 13/03/2025 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 98.75 | 0 | 0 | 50
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for BARAKAMALPUR water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001365/2022-2023 | 1371/ED | 14/03/2023 | 13/03/2024 | M/S S.S. ENTERPRISE | 130.31 | 98.37 | 75.49 | 70
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, T.W, Rising Main, FHTC For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000091/2023-2024 | 1355/HUG | 12/05/2023 | 01/04/2026 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 419.11 | 90.43 | 21.58 | 60
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | AUGMENTATION of BARAKAMALPUR (ZONE-I) Piped Water Supply Scheme with LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000092/2023-2024 | 1356/HUG | 12/05/2023 | 01/04/2026 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 310.94 | 42.31 | 13.61 | 80
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Construction of 900 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, T.W, LDS, Rising Main, FHTC & Construction of 4 Nos. Switch Room & Boundary wall at Proposed T.W Site For AUGMENTATION of BARAKAMALPUR (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000316/2023-2024 | 2391/HUG | 10/08/2023 | 26/12/2025 | P.B. ENTERPRISE (PINTU BHADURI) | 1034.2 | 312.15 | 30.18 | 15
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Construction of 4 Nos. Switch Room & Boundary wall at Proposed T.W Site For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000538/2023-2024 | 3105/HUG | 13/10/2023 | 01/06/2025 | T.K. INTERNATIONAL | 54.41 | 36.42 | 66.94 | 75
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 10/08/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 14.85 | 18.46 | 100
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Balance Laying Distribution System of proposed pipeline of BARAKAMALPURZONE-III Water Supply Scheme For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme underChandannagarSub-Division of Hooghly Division P.HE Dte. Block SINGUR,District:-Hooghly[AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000503/2023-2024 | 2902/HUG | 21/09/2023 | 20/12/2023 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 96.84 | 96.75 | 99.9 | 100
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Laying D.I Pipe& HDPE Pipe For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000547/2023-2024 | 3117/HUG | 16/10/2023 | 14/01/2024 | SURAJIT SINGHA RAY | 91.89 | 91.72 | 99.82 | 80
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Laying Distribution System of proposed pipeline of BARAKAMALPURZONE-III Water Supply Scheme For AUGMENTATION of BARAKAMALPUR (ZONE-III)PipedWater Supply Scheme under ChandannagarSub-Division of Hooghly Division P.HEDte.Block SINGUR, District:-Hooghly[AUGMENTATIONSCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000550/2023-2024 | 3153/HUG | 17/10/2023 | 15/01/2024 | M/S KAUSAR CONSTRUCTION | 93.46 | 93.41 | 99.95 | 100
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001023/2023-2024 | 3379/HUG | 21/11/2023 | 05/01/2024 | OSMAN SEKH | 64.2 | 15.88 | 24.73 | 100
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2022-2023 | 79/14/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 320.94 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000270/2022-2023 | 902/7/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 34.55 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 1383/16/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 77.76 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation for new service connection at Barakamalpur W/S Sch., Zone - II, T/W - III |  |  | BILL/04127/2023-2024 | 385 | 25/10/2023 | 25/10/2023 | WBSEDCL | 3.13 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-II, TW-IV |  |  | BILL/04131/2023-2024 | 384 | 25/10/2023 | 25/10/2023 | WBSEDCL | 5.89 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation for new service connection for Barakamalpur , Zone - III, T/W - I, Block Singur, Dist - hooghly |  |  | BILL/02760/2023-2024 | 173 | 10/08/2023 | 10/08/2023 | WBSEDCL | 3.52 | 0 | 0 | 0
23 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-II |  |  | BILL/04171/2023-2024 | 403 | 09/11/2023 | 09/11/2023 | WBSEDCL | 3.93 | 0 | 0 | 0
24 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-III |  |  | BILL/04170/2023-2024 | 404 | 09/11/2023 | 09/11/2023 | WBSEDCL | 3.23 | 0 | 0 | 0
25 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation for new service connection charge at Bora Kamalpur PWSS, Zone-II, TW - VI |  |  | BILL/04483/2023-2024 | 532 | 15/12/2023 | 15/12/2023 | WBSEDCL | 3.43 | 0 | 0 | 0
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Horizontal Auger boring with water jet system including Laying of additional pipe line at molla-simla & pahalanpur mouza For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. Block SINGUR, District-Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000303/2024-2025 | 3661/HUG | 13/11/2024 | 12/05/2025 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 59.69 | 5.35 | 8.96 | 70
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Withdrawing & relaying of distribution main at H/W site of Bora -Kamalpur (Zone - II) W/S Scheme under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000865/2023-2024 | 758/HUG | 05/03/2024 | 20/03/2024 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 2.98 | 2.97 | 99.85 | 100
28 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation for new service connection at Barakamalpur W/S Sch.[SM/12369], Zone - IV, T/W No. - I, (Gobindapur Dulepara), Block - Singur, Dt. - Hooghly under Nasibpur CCC, WBSEDCL, Ref. Id. - 503600456, Dated - 22-03-2024, Application No. - 5004079502 |  |  | BILL/00012/2024-2025 | 12 | 04/04/2024 | 04/04/2024 | WBSEDCL | 2.81 | 0 | 0 | 0
29 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-IV |  |  | BILL/04855/2023-2024 | 766 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.94 | 0 | 0 | 0
30 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-III |  |  | BILL/05993/2023-2024 | 805 | 27/02/2024 | 27/02/2024 | WBSEDCL | 5.78 | 0 | 0 | 0
31 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-I, TW-I & TW-II |  |  | BILL/04690/2023-2024 | 665 & 666 | 11/01/2024 | 11/01/2024 | WBSEDCL | 10.85 | 0 | 0 | 0
32 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR PWSS of Chandannagar Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001575/2025-2026 | 1475/Chan | 25/09/2025 | 02/10/2025 | AMBIAN INFRASTRUCTURE (PARTNERSHIP) | 0.95 | 0 | 0 | 0
33 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Horizontal Auger boring with water jet system including Laying of additional pipeline at Haripur mouza For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. Block SINGUR, District-Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001737/2024-2025 | 331/HUG | 05/02/2025 | 07/06/2025 | M/S KAUSAR CONSTRUCTION | 31.03 | 0 | 0 | 100
34 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Repairing of boundary wall at 2nd site of Barakamalpur PWSS Sceme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000294/2025-2026 | 927/CHAN | 21/07/2025 | 10/08/2025 | ASHA ENTERPRISE | 1.05 | 0 | 0 | 100
35 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Repairing of pump house at 1St and 2nd TW site of Borakamalpur PWSS under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000295/2025-2026 | 928/CHAN | 21/07/2025 | 10/08/2025 | ASHA ENTERPRISE | 4.47 | 0 | 0 | 100
36 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Quotation for new service connection at BARAKAMALPUR W/S Sch.[SM/12369], Zone - IV, T.W. No. - II, under Nasibpur CCC, WBSEDCL, Application No. - 5004526091, Dt. - 23/12/2024 , Ref. I.D. - 503833411 |  |  | BILL/02851/2024-2025 | 665 | 21/01/2025 | 21/01/2025 | WBSEDCL | 6.44 | 0 | 0 | 0
37 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Additional Quotation for service connection aat Barakamalpur W/S Sch. ,Zone-IV T.W. No.-II, [SM/12369], Block - Singur under Nasibpur CCC, WBSEDCL, Ref Id. - 860326649, Dt. - 5.02.2025, Application ID. - 100000131219 |  |  | BILL/03378/2024-2025 | 703 | 17/03/2025 | 17/03/2025 | WBSEDCL | 0.2 | 0 | 0 | 0
38 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | Addl. Quotation for new service connection at Barkamalpur W/S Sch. Zone - I, T.w. No. - II,Block - Singur,[SM/12369], under Nasibpur CCC, WBSEDCL, Ref. Id. - 860323933, Dt. - 16-01-2025, Application No. - 100000128283 for shifting of power from Pole to Pump House by one pole extension. |  |  | BILL/03100/2024-2025 | 690 | 31/01/2025 | 31/01/2025 | WBSEDCL | 0.26 | 0 | 0 | 0
39 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | SM/12369 | Augmentation | DAMAGE OF ROAD DURING LYING OF WATER SUPPLY PIPE LINE MAINLY CONNECTION OF DURGAPUR ROAD TO RASULPUR PACKAGE NO.WB-08-102 UNDER SINGUR BLOCK IN HOOGHLY DISTRICT. |  |  | BILL/00206/2025-2026 |  | 19/05/2025 | 19/05/2025 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 9.94 | 0 | 0 | 0
Total | [13 empty] | 3108.41 | 937.35 | 30.16