## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2022-2023 | 2686/14/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.36 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Route survey Design drawing & DPR preparation of Gopalnagar PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000167/2022-2023 | 262/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.11 | 97 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Sinking of Three Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at GOPALNAGAR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000456/2022-2023 | 2507/HUG | 22/11/2022 | 06/01/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 36.31 | 34.06 | 93.82 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2022-2023 | 01/06/Hug | 02/01/2023 | 02/01/2023 | Resource Division | 28.33 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000266/2022-2023 | 902/3/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 28.33 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000281/2023-2024 | 1383/30/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 28.33 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2022-2023 | 79/13/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 134.26 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch. TW-III |  |  | BILL/01453/2022-2023 | 211 | 24/03/2023 | 24/03/2023 | WBSEDCL | 0.7 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Quotation for new service connection at Gopalnagar W/S sch. , T/W - II, Dist. - Hooghly |  |  | BILL/00736/2023-2024 | 23 | 11/05/2023 | 11/05/2023 | WBSEDCL | 2.53 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Damages of Road from Dewanbheri to Paunan |  |  | BILL/00503/2023-2024 | BP-2023-24-415 | 29/09/2023 | 29/09/2023 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 15.81 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Revised Quotation Bill for New Service Connection at Gopal Nagar W/S. Sch. TW-IV |  |  | BILL/04070/2023-2024 | 338 | 10/10/2023 | 10/10/2023 | WBSEDCL | 0 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT GOPALNAGAR W/S SCH. , T/W NO. - IV, DIST. - HOOGHLY |  |  | BILL/00737/2023-2024 | 25 | 11/05/2023 | 11/05/2023 | WBSEDCL | 4.09 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | RESTORATION OF DAMAGES ROAD NAMELY DEWANBHERI TO PAWNAN PART OF DEWANBHERI KACHARIMORE TO BILATPUR BRIDGE VIDE PACKAGE NO. WB-08-ADB-172 |  |  | BILL/01560/2023-2024 | BP-2023-24-887 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 14.63 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Revised Quotation New service connection at Gopalnagar W/S Sch. , T/W No. - IV, Block - Singur, due to non payment of previous quotation for online banking transaction error. |  |  | BILL/04056/2023-2024 |  | 06/10/2023 | 06/10/2023 | WBSEDCL | 4.09 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | GOPALNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation under SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000053/2023-2024 | 1211/HUG | 27/04/2023 | 01/04/2026 | S. HATI | 499.95 | 262.58 | 52.52 | 90
16 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gopalnagar water supply scheme, T.W. No.- I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000211/2022-2023 | 838/ED | 14/02/2023 | 15/04/2025 | WEST BENGAL ENGINEERING CO. | 32.24 | 31.4 | 97.4 | 90
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | SM/12370 | Augmentation | Sinking of Tube Well, Rising Main, Construction of switch-room & boundary wall at Proposed TW site, Repairing of Switch Room, Boundary wall & FHTC For Augmentation of GOPALNAGAR Piped Water Supply Scheme under SINGUR Block under Chandannagar Sub-Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000801/2022-2023 | 952/HUG | 30/03/2023 | 01/08/2025 | LOKENIRMAN | 246.68 | 215.88 | 87.51 | 85
Total | [13 empty] | 1080.88 | 548.03 | 50.7